## Andersen.MCBCB
Project Number | Project Title | FY Execution | DoD Effect Determination | Historic Properties Directly Affected | Historic Properties Indirectly Affected | FEIS/Original Survey Reference | Status: Current as of December 2024
Andersen Air Force Base - North Ramp
J‐001 (Original) J-001A (New) | U&SI Mass Grub and Grade Phase 1 Ace Gate, GoJ (Original) RC2014-0625 AAFB ACE Gate and Facilities (New) RC2011-88321/PA | 2010 (Original) 2011 (New) | Adverse Effect | 66-08-2552 | None | Dixon and Walker 2011 | Consultation completed upon signing of 2011 Military Relocation PA. Adverse effect mitigated via archeological data recovery (Stipulation VI.1.b.) under MILCON P-100, preparation of Public Education and Interpretation materials (Stipulation VI.B.) and update of Guam Historic Properties Information data form (Stipulation VI.G.), completed May 2013. Construction complete.
P-100 | AAFB North Ramp Utilities Increment 1 RC2011-8831; also RC2011-8835/8836/36c (included P101 review) | 2010 (Original) 2011 (New) | Adverse Effect | 66‐07‐1064 (North Field), 66-08-2305, 66-08-2551, 66-08-2552 | None | 66-07-1064: GHPI Data Form, 1975 66-08-2305: Welch 2010 66-08-2551: Dixon and Walker 2011 66-08-2552: Dixon and Walker 2011 | Consultation completed upon signing of 2011 Military Relocation PA. Adverse effect mitigated via preparation of Historic American Engineering Record (HAER) Survey of GHPI Site 66-07-1064 (North Field), archeological data recovery (Stipulation VI.1.b.) of GHPI Sites 66-08-2305, -2551 and -2552, preparation of Public Education and Interpretation materials (Stipulation VI.B.) and update of Guam Historic Properties Information data forms (Stipulation VI.G.), completed May 2013. Construction Completed.
P-100A (Original) J-200 (New) | AAFB North Ramp Utilities, Increment 2 (Original) RC2011-8835/8836 AAFB North Ramp Utilities II (New)RC2013-0904 | 2012 (Original) 2014 (New) | Adverse Effect | 66‐07‐1064 (North Field) | None | GHPI Data Form, 1975 | Consultation completed upon signing of 2011 Military Relocation PA. Adverse effect mitigated via preparation of Historic American Engineering Record (HAER) Survey of GHPI Site 66-07-1064 (North Field), archeological data recovery (Stipulation VI.1.b.) of GHPI Sites 66-08-2305, -2551 and -2552, preparation of Public Education and Interpretation materials (Stipulation VI.B.) and update of Guam Historic Properties Information data forms (Stipulation VI.G.), completed May 2013. Structured archeological monitoring will also occur during intrusive activity. Construction completed. J-200 Phase 2 and Phase 3 projects in planning phases.
P-101 (Original) P‐101/P-101A (New) | North Ramp Parking, Increments 1 and 2 (Original) RC2011/8835/8836 AAFB North Ramp Parking Increments 1 and 2 (New) | 2010 (Original) 2011 (New) | Adverse Effect | 66‐07‐1064 (North Field) | None | GHPI Data Form, 1975 | Consultation completed upon signing of 2011 Military Relocation PA. Adverse effect mitigated via preparation of Historic American Engineering Record (HAER) Survey of GHPI Site 66-07-1064 (North Field), archeological data recovery (Stipulation VI.1.b.) of GHPI Sites 66-08-2305, -2551 and -2552, preparation of Public Education and Interpretation materials (Stipulation VI.B.) and update of Guam Historic Properties Information data forms (Stipulation VI.G.), completed May 2013. Construction completed.
Unassigned | North Ramp Design Studies (New) RC2013-1114 | 2014 | Adverse Effect | 66‐07‐1064 (North Field) | None | GHPI Data Form, 1975 | SHPO concurred with Determination of Effect on 5 August 2014. Consultations Completed. This PA Memo covered all future design efforts in the N. Ramp area.
P-109 | VMM Hangar #1 (Original) Aircraft Hangar #1 (New) RC2013-0827 | 2012 (Original) 2014 (New) | Adverse Effect | 66‐07‐1064 (North Field) | None | GHPI Data Form, 1975 | SHPO concurred with Determination of Effect on October 15, 2013. Adverse effect mitigated via preparation of Historic American Engineering Record (HAER) Survey of GHPI Site 66-07-1064 (North Field), preparation of Public Education and Interpretation materials (Stipulation VI.B.) and update of Guam Historic Properties Information data form (Stipulation VI.G.), completed May 2013.
Unassigned (Original) P-230 (New) | GSE Shop/Shed, AV Armament/Life Supp & LOX Pad (Original) GSE Shops (New) RC2014-0673 | 2014 (Original) 2015 (New) | Adverse Effect | 66‐07‐1064 (North Field) | None | GHPI Data Form, 1975 | SHPO concurred with Determination of Effect on 15 August 2014. Consultation has been completed.
Unassigned (Original) P-240 (New) | MWSS Elec Comm & Flightline Armory (Original) MWSS Facilities (New) RC2014-0838 | Unscheduled (Original) 2015 (New) | Adverse Effect | 66‐07‐1064 (North Field) | None | GHPI Data Form, 1975 | SHPO concurred with Determination of Effect on 6 November 2014. On 4 November 2014, NFM responded to SHPO request for monitoring at P240 stating that monitoring was not needed because of demonstrated shallow soils and absence of cultural material in several referenced surveys. SHPO response agreed that there was shallow soil and concluded that the project could be monitored without submitting a formal AMDP for review. Consultation has been completed.
P-601 | Transient Squadron Hangar #2 (Original) Aircraft Hangar #2 (New) RC2016-0039 | 2013 (Original) 2018 (New) | No historic properties affected ("no historic properties remain to be affected" - refers to previous obliteration of portion of North Field by site preparation activities) | None | None | Welch 2010 | future project under 2010 Record of Decision; Sec. 106 consultation complete RC2016-0039, dated Dec. 28, 2015. Currently wrapping up construction (building interior only, no exterior work)
P-250 | MALS Facility RC2016-0124 | 2018 (New) | No historic properties affected ("no historic properties remain to be affected" - refers to previous obliteration of portion of North Field by site preparation activities) | None | None | Welch 2010 | SHPO concurrence with DoD determination that no historic properties are affected ("no historic properties remain to be affected" in letter (RC2016-0124) dated March 2, 2016. Consultations have been completed.
P-260 | Corrosion Control Hangar RC2016-0125 | 2018 (New) | No historic properties affected ("no historic properties remain to be affected" - refers to previous obliteration of portion of North Field by site preparation activities) | None | None | Welch 2010 | SHPO concurrence with DoD determination that no historic properties are affected ("no historic properties remain to be affected" in letter (RC2016-0125) dated March 3, 2016. Consultations have been completed.
Unassigned (Original) P-280 (New) | Aircraft/Line Ops Building (Original) Air Ops Building (New) | Unscheduled (Original) Confirmed 2022 Project | No Historic Properties Affected | None | None | Welch 2010 | PA Memo delivered on 3/30/2021. SHPO concurred with determination. Construction underway.
J-201 now P-201 | Aviation Instruction Facility, North Ramp AAFB | 2026 (New) | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Welch 2010 | future project under 2010 Record of Decision PROJECT CANCELLED
P-270 | ACE Gym and Dining P-270 RC 2019-0011 | 2019 | PA Memo 1 delivered 10/05/18; SHPO concurrence with no historic properties affected (RC2019-0011) |  |  | Davis 1983, Dixon et al. 2015, Grant et al. 2007, Liston 1996, Mohlman 2015, Salo and Mohlman 2012, Tuggle 1993, Welch 2010, Yoklavich and Tuggle 2004 | consultation completed; construction nearing completion (building interor only, no exterior work).
J-200 II | AAFB North Ramp Utilities II - Communication Line | 2024 | PA Memo 1 delivered 11/17/2020 | None | None | Aaron et al 2007, Athens 2009, Church et al 2009, Davis 1983, Defant 2006, Dixon, Wlaker 2011, Dixon et al 2011b, Dixon et al 2014a, Dixon 2015, Grant et al 2007, Haun 1988, Haun 1989, Hlatky et al 2018, Hokanson et al 2007, Hunter-Andersn et al 2003, Kurashina et al 1986, Liston 1996, Mason Archtects 2004, Mohlman 2015, Welch 2010, Yee et al 2004 | Project in design phase. Construction contract awarded. PA memo submitted 22 NOV 24, SHPO concurrence received 25 NOV 24
P-295 | Ordnance Ops RC2017-0879 | 2020 | PA Memo 1 delivered 4/06/2018; SHPO comments dated 5/22/2018 with non-concurrence; JRM addressed SHPO comments; , maintain that there are no historic properties affected. | n/a | n/a | TBD | In design phase; PA Memo to be developed FY17. archeological survey contract has been awarded for the project. archeological work plan delivered to SHPO 2/2/18. Survey completed; Draft archeological report delivered to SHPO 2/02/2018; no comments received. Final technical report and GIS data delivered 4/19/2018. PA Memo 1 delivered 4/06/2018. SHPO non-concurrence received 5/22/2018. DON response to SHPO 7/18/2018 maintaining determination that no historic properties will be affected. Construction nearing completion.
P-296 | Ordnance Ops Admin (RC2019-0028) | 2021 (New) | No Historic Properties Affected | None | None | Athens 2009, Dixon et al. 2014, Mohlman 2013 | PA Memo 1 Design Studies delivered 11/05/2018; SHPO comments dated 12/31/2018 with concerns; JRM addressed SHPO comments; site of concern outside of APE. In design phase; PA Memo 1 completed for design studies 1/11/2019. Construction planned Beyond FY20. UPDATE: Construction PA Memo #1 was presented to SHPO on 8/4/20 with determination of No Historic Properties Affected. No comments were received from SHPO. Update: PA Memo 1 for construction delivered on 8/4/2020. DON agreed to SHPO request to have an archeologist provide checks and photographs during initial ground disturbance. There were subsequent changes (inclusion of utility line) in the APE requiring a new PA Memo. No comment was received on the revised PA Memo. Monitoring of grond disturbance has been completed with no discoveries.
P-290 | ECM (MSA) RC2017-0605 | 2022 (New) | Revised PA Memo 1 determination of no adverse effect as a result of conditions to avoid the sites. | N/A | N/A | TBD | PA Memo #1 determined adverse effect on two sites. PA Memo #2 currently in preparation; adverse effect will be avoided by protection of the sites during construction and preservation in place. PA Memo #2 delivered to SHPO 7/13/17. DON agreed to additional survey requested by SHPO. Work plan for survey will be provided to SHPO. Draft work plan delivered 4/12/2018; SHPO commented 6/5/2018; Final work plan addressing SHPO comments delivered 7/12/2018. Surveys completed and PA Memo 1 (Revised) with determination of no adverse effect. Construction is planned for FY19. Final Technical Report delivered February 2019. Construction in preparation; adjacent archaelogical sites protected by fencing installed under supervision of Camp Blaz archaeologist. Notification of post-construction discovery including human remains was made. Construction started late 2022 with spot checks by MCBCB archeologists. Field work complete at all 5 data recovery sites 3 have been released for construction. Field work complete at 4 of the 5 human remains sites, 3 have been released for construction. HR recovery field work completed and balance of data recovery sites (2) and HR sites (2) released for construction by Feb 2024.
Andersen Air Force Base - Main Base
Unassigned | Elementary School | Beyond FY22 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | future project
P-415 | Child Development Center | FY24 | No Historic Properties Affected | None | None | Davis 1982, Dixon 2014, Welch 2010 | PA memo for construction completed April 2024.
P-403 | Middle School - Expansion | Beyond FY22 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | future project
P-411 | Youth Center | FY25 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | PA memo for construction in future
P-413 | Temporary Lodging Facility | FY27 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | PA memo for construction in future
H-279 | Family Housing | Multi-Phase FY21 and Beyond | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | H-279: multi-phase demolition and construction of military family housing was previously consulted on (27 Oct 2015 with concurrence with DoD determination of no historic properties affected. H-280 is construction of new family housing within the APE consulted on under H-279. Additional APE for utilities anticipated in future PA Memo. Increase in APE to accomodate utility installation required supplemental PA Memo. Transmittal on 7/28/2022. H-308 is next phase of new familing housing within the APE consulted on under H-279, construction award in FY24. This phase will require an increase in APE to accomodate construction of stomrwater controls Revised PA memo posted for review 8 SEP 23, no comments, complete 30 OCT 23.
Marine Corps Base Camp Blaz - Live Fire Training Range Complex (formerly Northwest Field)
P-715 | KD Ranges - LFTRC (RC2012-10751) | 2016 | Adverse Effect | Further consultations were conducted under Range Mitigation Plan resulting in data recovery on 14 archeological sites | Further consultation under Range Mitigation Plan identified sites in the SDZ; a representative sample of these sites will be selected for pre-construction documentation and monitoring for two years during construction and operation of the ranges. In addition, SHPO identified a set of sites for which additional research was requested. Navy provided a report in March 2016 addressing concerns on the sites and subsequently provided an addendum (July 2016) containing additional information obtained from the National Archives, Washington, DC. | Church 2009, Dixon 2014, Dixon et al. (2011, 2012), Kurashina et al. 1987, Welch 2010 | Navy received concurrence from SHPO that the information provided satisfies concerns about the sites in question. archeological fieldwork was completed in June 2016; draft technical report and draft public information document were delivered to SHPO for review January 24, 2016. Recommended treatment of human bone found during lab analysis was provided by SHPO. Bone was treated as artifact but bagged separately and protected by padding. Next actions: consult on SDZ signage, complete final report and Public information booklet; translate booklet into Chamorro language. Collect baseline data on sites to be monitored. MCAG archeologists collected baseline data from sites near construction footprint and sites on FWS land. Final technical report was delivered to SHPO on 11/16/2017; educational booklets (50 English and 50 Chamorro versions) were delivered to SHPO 2/15/18. Design review of P715 clear and grade plans and Rt 3A highway improvements (both consulted under RMP) was completed Aug 7, 2018. As of 2019, P-715 is an area covered by the Dispute Resolution Agreement of July 2018. Construction is in progress and monitors are present. As of August 2019, inadvertent discoveries have been made in the KDRR, MRFR, and range road. Inadvertent Discovery protocol was followed; Contracted archeologists are at work on data recovery. As of 2020, all inadvertent discoveries have been data recovered and all human remains have been recovered. archeological monitoring has concluded. Construction completed.
P-715 (New) | Installation of Ungulate Fencing for Ungulate Control Areas (new) | 2016 (New) | No Adverse Effect | None | None | Church 2009, Dixon 2014, Dixon et al. (2011, 2012) | Biological Opinion requirement under Endangered Species Act. 2019 update: PAM 1 delivered April 2019; SHPO did not concur with No Historic Properties, preferred No Adverse Effect. PAM 2 delivered 7/8/19 with revised determination per SHPO recommendation. SHPO concurrence 8/6/19. archeologists completed pre-construction inspection of the ungulate fencing corridor on 9/15/20. Identified soil and rock outcrop areas, noted observed artifact locations; soil areas will be monitored during fence installation, and; document and avoid any sites encountered, if practicable. archeological monitoring for this work has concluded. Initial fence installation complete, installation of additional fence to secure gap next to edge of cliff required.
P-715 (New) | SDZ Lighting and Signs | 2021 | No Adverse Effect | None | None | Church 2009, Dixon 2014, Dixon et al. (2011, 2012), Kurashina et al. 1987, Welch 2010 | PA Memo submitted on 3/5/2021. No comments received. Installation of signage completed.
P-735 | Machine Gun Range (RC2019-0053) | Beyond FY21 | Adverse Effect | Adverse effects on historic properties directly affected were mitigated through archeological data recovery, per the 2011 PA. Historic properties included those discovered by pre-construction surveys and those discovered during construction by monitoring agreed on in the 2020 Dispute Resolution Agreement. | Indirectly Affected historic properties include those within and underlying the SDZ. The adverse effect is primarily loss of access while range is in operation. | Church 2009, Dixon 2014, Dixon et al. (2011, 2012), Kurashina et al. 1987, Welch 2010 | Initial design review package was delivered to SHPO 12/13/2018 for 45 days review period, which ended 1/28/2019 without comment. Additional review of 60% design is pending. Construction is planned for FY19. Delivery for 15 day review of 60% drawings April 2019. No comments received; however, email from SHPO to PAC stated there were no concerns. Note: P735 was not referenced in the 2018 Dispute; however, SHPO assumed that all LFTRC was included. We anticipate effort by SHPO to extend monitoring requirement into P735. 5/26/20- SHPO and Navy in discussion to included monitoring in P-735 (either through Stip XIII or Navy incorporating into requirements as proactive approach). SHPO initiated Dispute 7/30/2020; resolution included supplemental survey prior to construction and monitoring during construction. Details are being worked out at time of this report. Range signage design reviews will be provided to SHPO in FY21. Stipulation XIII Resolution letter was signed on 10/30/2020. DON submitted Pre-final archeological Survey, Monitoring, and Discovery Plan (AMDP) on 11/17/2020. SHPO commented on Pre-Final AMDP on 1/20/2021. DON responded and resolved SHPO’s comments, and provided final work plan on 3/15/2021. archeological survey fieldwork was completed following the approved work plan which used treatments specific for karst and cobbly loam areas. No sites were found in the karst area; sites were found in the cobbly loam area and were subsequently investigated. Draft report was received. Monitoring continues in remaining areas undergoing ground disturbance. One location with scattered fragments of human bone was investigated and investigation has been completed. Monitoring in other areas continues, including cycad salvage areas. Construction vegetation clearance nearing competion.
Marine Corps Base Guam - Urban Training Complex (formerly Andersen South)
Unassigned | Andersen South Design Studies (New) RC2013-1101 | 2014 | No Adverse Effect | 66-04-2324, 66-04-2325, AS-T-2008-01, AS-T-2008-04, 66-04-2326 | None | Welch 2010 Dixon, Walker and Carson 2011 | Submitted as J755 Design Studies. No Adverse Effect determination due to protection of four historic properties in APE by high visibility fencing. Revised PA Memo #2 was delivered August 31, 2016. Revisions included communication ducts and proposed further evaluation of an additional historic property (04-2326), possibly associated with former Army hospital. SHPO comments led to revised figures, which were delivered Oct 19, 2016. SHPO concurrence received Oct 26.
Unassigned (Original) J-755 (New) | MOUT Facility/Rappelling, Phase 1 (Original) Urban Combat Training (Previous) Andersen South Training Complex (New) RC2013-1101 | 2014 (Original) 2018 (New) | Adverse Effect | TBD: Further Consultation Required regarding eligibility and mitigation of adverse effects on eligible sites | Further Consultation Required | Welch 2010 Dixon, Walker and Carson 2011 | PA Memo #1 for construction and operation was delivered March 9, 2017. PA Memo #2 was delivered June 5, 2017. Includes MOUT Facility/Rappelling Phase 2, Company Level Maneuver, General Improvements/ Breaching House, and Driver Convoy Course. In addition, APE will include entirety of Andy South to accomodate company level maneuver training. Some sites will be affected. MCAG (now Marine Corps Base Camp Blaz) received SHPO staff comments on 8/24/17 and responded on 11/16/17. Following discussion with SHPO, MCAG submitted a third PAM which clarifies that PA Memo 2 responded to comments by the State archeologist, not SHPO. PA Memo 3 responds to official SHPO comments and clarifies that construction and operation are being consulted on separately. MCAG archeologists visited specific former lancho locations near the construction footprint that were called out by SHPO and confirmed that there are no known eligible sites within the construction footprint. Sites within the operations footprint will be consulted on with a future PA Memo. 2019 update: J755 was included in 2018 Dispute Resolution Agreement; geotech work is underway with monitor. The APE in the construction PA memo does not include all of Andersen South. Refer to Andersen South Operations. 2020 UPDATE: Construction work is monitored under 2018 Dispute Resolution Agreement. 16 archelogical discovery areas have been discoverd as of this report. Most are within CVOC in western part of Andy South. Camp Blaz EV is working with consultant in an effort to avoid and preserve in place eligible sites in the CVOC where possible. Several locations containing one or more human burials were discovered. Investigation of multiple burials in HR-5 has concluded. A Burial Treatment Plan for avoiding the burials and preserving them in place is being reviewed. Construction nearing completion, archeological monitoring continuing as required. Investigation of burials at HR-8 and HR-15 completed. Human remains exposed (HR-16) as a result of typhoon Mawar effects have been addressed.
P-330 | Explotation Facility | 2028 | TBD | TBD | TBD | TBD
N/A | Urban Training Complex Operations (RC2013-1101) | Beyond FY22 | No Adverse Effect | Limited site investigations and a site eligibility determination planned | Further Consultation Required via PA Process | Welch 2010 Dixon, Walker and Carson 2011 | PAM 1 for operations was delivered August 2019 and SHPO comments responded to. PAM2 prep in progress. The APE for Andersen South Operations includes the area to be used for future training activities. Limited investigations and a site eligibility determination planned to addressed to avoid adverse site effects. archeological investigations to confirm boundaries of archeological areas discovered during construction have been contracted. Investigation will include work at lancho sites indicated on historical maps.

## Naval Base Guam.MCBCB
Project Number | Project Title | FY Execution | DoD Effect Determination | Historic Properties Directly Affected | Historic Properties Indirectly Affected | FEIS/Original Survey Reference | Status: Current as of December 2024
Naval Base Guam - Apra Harbor
P-1003 | Apra Harbor Military Working Dog Relocation (Original) Military Working Dog Relocation (New) | 2010 | No Historic Properties Affected | N/A | N/A | Dixon, Walker and Carson 2011 | Consultation completed upon signing of 2011 Military Relocation PA. Mitigation not required. Construction Completed.
P-204 | Apra Harbor Wharf Improvements, Increments 1 and 2 (Original) Apra Harbor Infrastructure (New) | 2010 | No Historic Properties Affected | N/A | N/A | Mason Architects Inc. and Weitze Research 2010 | Consultation completed upon signing of 2011 Military Relocation PA. Mitigation not required. Construction Completed.
J-001 | U&SI Mass Grub and Grade, Phase 1 (GoJ) [Secondary Access Road] (Original) Apra Harbor Infrastructure (New) | 2010 | No Historic Properties Affected | N/A | N/A | Athens 2009 Welch 2010 Dixon and Walker 2011 Dixon, Walker and Carson 2011 | Consultation completed upon signing of 2011 Military Relocation PA. Mitigation not required. Construction complete.
J-006 | Apra Harbor Dental/Medical Clinic (Original) Apra Medical Clinic (New) RC2011-7959 | 2011 (Original) 2018 (New) | No Adverse Effect No Historic Properties Affected | N/A | N/A | Athens 2009 Welch 2010 Dixon and Walker 2011 Dixon, Walker and Carson 2011 | Consultation completed upon signing of 2011 Military Relocation PA. Mitigation not required. In design. New information: Revised PA Memo concurred upon by the SHPO, with condition for site checks of added utility corridor. Areas to be monitored included a north/south line parallel to a road and trenching in the dirt road adjacent to the Japanese Amphitheater, a stone wall and drainage features along the road. Trenching along road near amphitheater paused when old fuel line was encountered. More than 2 meters of fill exposed. As of Sept 2020 trenching remained on hold. Spot checks will continue along road by amphitheater; most recent spot check was March 2021 with no changes noted. Report will follow conclusion of trenching. March 2021 Trenching and monitoring resumed along the dirt road. MCBCB archaeologist observed more than 2 meters depth of fill in trench, with no visible base of fill. April through June 2021: contractor completed trenching, removal of old pipes, installation of ductwork and backfilling trench. No damage was observed during excavation and laying of new ductwork; however, rock wall and rock lined ditch were scraped during backfilling and site clean-up. Corrective Action Plan is required. Corrective action plan submitted to SHPO August 2021. SHPO responded in late September 2021 with a request for additional information. Approved Corrective Action Plan was followed and final inspection was completed. Report was sent to SHPO. Clinic construction completed. MCBCB provided copies of background documents to SHPO relating to historic site.
J-007 | Apra Harbor Waterfront HQ Building (Original) Waterfront HQ Building (New) | 2011 (Original) 2017 (New) | No Historic Properties Affected | N/A | N/A | Athens 2009 Welch 2010 Dixon and Walker 2011 Dixon, Walker and Carson 2011 | Consultation completed upon signing of 2011 Military Relocation PA. Mitigation not required. In design. Construction pending. Construction underway. Two large anchors (one US, the other Japanese) discovered during wharf improvement projects will be displayed on the building grounds. Pad for anchor exhibit has already been poured and anchors have been brought to project site. Unfortunately, the large US anchor was accidentally sold for scrap; the display contains two Japanese anchors. Construction completed.
P-600 (Original) J-609 (New) | Apra Harbor Embark Ops (Original) Apra Embark Facility (New) | 2013 (Original) FY23 (New) | No Historic Properties Affected | none | none | Welch 2010 | Project under 2010 Record of Decision. PA Memo for Design submitted for SHPO review on June 11, 2020. No comments were received from SHPO. PA Memo for Construction currently in progress. To be presented for review in next reporting period. PA Memo for Construction submitted in September 2022, resolving SHPO comments. SHPO did not concur with MCBCB finding of no historic properties affected and recommended archaeological monitoring. MCBCB provided additional evidence demonstrating that up to 6 meters of fill covers the project area. Consultation continues, comment resolution completed with site visit in June 2023. J-609 construction will avoid Japanese POW steps located within the project footprint.
Marine Corps Base Camp Blaz - Finegayan
J-001 (Original) J‐001B (New) | U&SI Mass Grub and Grade, Phase 1 (GoJ) (Original) Finegayan Utilities and Site Improvements Phase 1 (New) RC2014-0625 | 2011 (Original) 2017 (New) | Adverse Effect | 66-08-2295, 66-08-2297, 66-08-2298, 66-08-2303, 66-08-2307 (Original) 66-08-1350, 66-08-2302, 66-08-2303, 66-08-2305, 66-08-2306, 66-08-2307, 66-08-2308, 66-08-2309 (New) | 66-08-0007 | Athens 2009 Welch 2010 Athens 2009, Dixon et al 2011, Haun 1988, Highness and Haun 1990, Kurashina et al. 1987, Kurashina et al. 1988, Olmo et al. 2000, Reinman 1977, Welch 2010 | Consultation for original APE completed upon signing of 2011 Military Relocation PA. PAM 2 delivered Dec 9, 2014. SHPO comments on PA Memo 2 received on Jan. 23, 2015 (RC 2014-0625), NFM staff met with SHPO Jan 29 to discuss comments and work to resolve issues. Data recovery was completed at 9 original sites. U&SI work is currently in progress. J-001B is one of four areas being monitored under 2018 Dispute Resolution agreement. As of 5/26/2020: Fieldwork completed at additional 8 discoveries. 3 areas of human remains are under investigation. Supplemental data recovery of 10 features are ongoing within Site 66-08-2303. In-situ burials in HR1 will be preserved in place at Camp Blaz. A monument patterened after the Layon Landfill monument will be placed at the grave site, along with a crypt to contain non-burial context remains. Area E, ca. 18 acres located immediately north of the base entrance was cleared. Monitors discovered two discoveries (inadvertent discoveries 9 and 10) and three locations with non-burial bone fragmernts. Archaeological investigations are projected to be complete in Area E by mid October 2020. Archaeological Discovery Area 11 (J-001B-11) in Area D was confirmed on 4/5/2021 and reported to SHPO and ACHP per the 2011 PA. As of Dec. 2021, archaeological investigations in the monument area were finished and shaping of the HR-1 monument area was nearing completion. The monument and crypt were ready for installation and the completed plaques had been delivered. Monitoring within J-001B continued; additional bone discoveries had been made in Area D. The number of HR discoveries had reached 20. As of June 2022, monitoring within J-001B had continued, the number of HR discoveries had reached 26, the construction contractor had completed the construction at the HR-1 memorial area (31 March 22), and we were working with the MILCON project teams to develop a plan to mitigate human remains in a burial context at five of the dscoveries in Area D. As of Dec 2022, monitoring was on-going as required. Preservation in plac of the human remains in burial context at Area D had been selected and a burial treatment plan was being prepred. All current human remains recovery work had been completed. Sabanan Fadang Burial treatment plan (HR-1) signed by SHPO and JRM in September 2022. Addendum to the Sabanan Fadang burial treatment plan (Area D) was finalized in June 2023. Blessing of the Area D burial sites conducted on 27 JUL 23. Developed plan for baskets to contain human remains recovered but not associated with a burial for reburial. SHPO coordinated public review of those comments; contractor currently preparing those remains for reburial along with recovering of Area D burials with soil. Ceremony for burials held on 5 APR 24 and archaeological recovered the burials with topsoil from the site afterwards. Balance of work to be done by P-325 project.
J-001B (New) | Installation of Ungulate Fencing for forest enhancement areas (new) RC2014-0625, CR RC2014-0291 | 2015 (New) | No Historic Properties Affected | None | None | Welch 2010 | SHPO concurred with Determination of Effect on Feb 2, 2016 (RC2016-0048). Consultation has been completed.
J-001B (New) | Area F Expansion RC2016-0048 | 2021 | No Historic Properties Affected | None | None | Welch 2010 | On 2/26/21 a revised PA Memo #1 for J-001B Area F was delivered. The revised PA Memo indicates an increase of the APE from 5.4 acres to 9.8 acres in order to accommodate a required stormwater infiltration basin at Naval Base Telecommunication Site (NBGTS). The initial PA Memo #1 delivered on January 21, 2021. Revised PA Memo #1 for J-001B Area F indicating an increase of the APE from 5.4 acres to 9.8 acres was submitted to SHPO on February 26, 2021. Comment period for the Revised PA Memo ended April 12, 2021. DON determined that no historic properties will be affected by the expansion. April 2021, SHPO provided comments to Revised PA Memo # 1 and DON responded. In accordance with the 2018 Stipulation XIII, work in this area will be monitored by any archaeologist.
1147910 (New) | Establishment of Native Plant Nurseries RC2016-0014 | 2015 (New) | No Historic Properties Affected | none | none | Athens 2009 Welch 2010 Kurashina et al. 1987 | SHPO concurred with Determination of Effect on 16 December 2015. SHPO noted in their correspondence that PA Memos are not "addendums" to 2011 PA and Navy will ensure that this terminology is not used in future PA Memos. Consultation has been completed.
P‐113 (Original) J-017 (New) | U&SI Mass Grub and Grade, Phase 2 (US) (Original) Finegayan Utilities and Site Improvements Phase 2 (New) | 2012 (Original) 2019 (New) | Adverse Effect (as originally scoped) | 66-08-2295, 66-08-2297, 66-08-2298, 66-08-2303, 66-08-2307 (Original) 66-08-1350, 66-08-2308 (New) | 66-08-0007 | Reinman 1977 Kurashina, McGrath and Manner 1987 Haun 1988 Highness and Haun 1990 Olmo, Mangieri, Welch and Dye 2000 Athens 2009 Welch 2010 | Consultation for original APE completed upon signing of 2011 Military Relocation PA. New Information consultation (Stipulation IV.F.) for new APE on hold. In design. 2019 update: Project has been separated into multiple phases; new J-017 -2 will have different APE from that previously consulted on. Other related projects will be listed separately. Determinations of effect will change,
Forest Enhancement | Installation of Ungulate Fencing for forest enhancement areas | 2024 | No Historic Properties Affected | None | None | Welch 2010 | In consultation with USFWS Planned for FY19. Divided into multiple projects that will be conslted on separately. Supplemental PA Memo for MCBCB Forest Enhancement Sites (FES) – Installation of ungulate fence and design studies and construction of irrigation wells (RC 2022-0952). PA memo Rev 1 (water well construciton) posted for review 11 JUL 23, no comments, complete 11 SEP 23.
J-017-II | Main and Commercial Gates (RC2007-0782 and RC2020-0605) | 2020 (NEW) | No Historic Properties Affected | None | None |  | Consultations with SHPO completed in 2020
J-017-V | Waterline Interconnect DESIGN STUDIES. | FY25 | No Historic Properties Affected | none | none | Welch 2010 | Proposed interconnected waterline and upgrades to an existing pump facility, a potential new pump facility, and potable water mains to connect existing water wells and a water tank in support of water infrastructure at Marine Corps Base Camp Blaz Design studies only, at this time. APE changed now includes area outside J-001B APE, revised PA memo for design studies completed. PA memo for construction required in future. Archaeological monitoring per 2018 Resolution Agreement.
J-017-I and III | Communication Cabling and Area Distribution Node (ADNSTC)(RC2020-0605) | 2020 (NEW) | No Adverse Effect | None | None |  | J-017-I and J-017-III were combined into a single construction project (J-I&III ADNSTC). PA Memo delivered June 1, 2020. SHPO non-concurrence on 6/25/2020, referencing J-001B-002 where preservation in place of human remains was under consideration. DON responded that comments made on Gates project (J-017-ll) applied to this project as well.
J-011 | Base Headquarters (Original) Base Admin and Comm (New) | 2011 (Original) FY21 (New) | No Historic Properties Affected | none | none | Welch 2010 | Combined with J-025 (Mamizu vertical project) and PA Memo delivered on 2/17/2021. All projects within the J-001B project footprint have already been mitigated.
J-031 J-016 | Bachelor Enlisted Quarters 1 ‐ 3 (Original) Bachelor Enlisted Quarters (New) - 1 Building | 2011 (Original) FY20 | No Historic Properties Affected | none | none | Welch 2010 | Located within J-001B footprint. Geotech work was proposed ahead of J-001B U&SI work. Navy consulted with SHPO, who concurred that consultations for J-001B covered the proposed geotech work on J-016. PA memo for construction will be prepared in the future. Planned for FY19, PA Memo will consult on J016 and J-030, which will be awarded in the same construction contract. 2019 update: instead of J-016 and J-030, the first multiple vertical construction consultation is for J-031, J-033, P-311, P804 and P-459. PA memo was delivered 7/8/19; SHPO did not concur. Response to SHPO comments pending from Navy. Note name changes: J-016 became J031 andJ030 became J031. Both were included in multiple vertical property consultations that SHPO objected to. DON responded to SHPO objections on 6/16/20, addressing objections that referenced historic properties that had been, or were being data recovered.
P-305 | 4th Marines Reg Fac | FY22 | No Historic Properties Affected | none | none | Athens 2009, Welch 2010 | Future project within J001B APE. Combined into one PA Memo (MILCON Verticals Stage 1) with P-306, P-307, P-310, P-314, P-326, P-802, and P-803. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period. PA Memo delivered June 8, 2021.
P-306 | CLB-4 Fac | FY22 | No Historic Properties Affected | none | none | Athens 2009, Welch 2010 | Future project within J001B APE. Combined into one PA Memo (MILCON Verticals Stage 1) with P-305, P-307, P-310, P-314, P-326, P-802, and P-803. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period.
Unassigned (Original) P-307 (New) | III MEF Armory (Original) Consolidated Armory (New) | 2014 (Original) FY22 (New) | No Historic Properties Affected | none | none | Welch 2010 | Future project within J001B APE. Combined into one PA Memo (MILCON Verticals Stage 1) with P-305, P-306, P-310, P-314, P-326, P-802, and P-803. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period. PA Memo delivered June 8, 2021.
P-308 | Law Enf Bn Co | N/A | N/A | N/A | N/A | Welch 2010 | Project cancelled
P-309 | GCE Inf Bn 1 and 2 Fac | 2023 (New) | No Historic Properties Affected | J-001B-002, J-001B-009, J-001B-010, J-001B-011, HR-12, HR-20, HR-22, HR-25 | none | Athens 2009, Pacheco et al. 2020, Welch 2010 | Vertical project Combined with P324 and P325; PA Memo posted 2 FEB 2022, finalized 10 JUN 2022.
P-310 | Infantry Battalion Company Headquarters | FY22 | No Historic Properties Affected | none | none | Welch 2010 | Future project within J001B APE. Combined into one PA Memo (MILCON Verticals Stage 1) with P-305, P-306, P-307, P-314, P-326, P-802, and P-803. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period. PA Memo posted June 2021
P-311 | Central Fuel Station | 2018 (Original) FY21 (New) | No Historic Properties Affected | none | none | Athens 2009, Welch 2010 | Project was included in multiple vertical construction consultation (P-311, P-312, P-317, and P-804 Multiple Vertical Projects). PA Memo for design and construction delivered 7/8/19. New PA Memo for design and construction submitted on 03/02/2021.
P-314 | MEB Enablers | FY22 | No Historic Properties Affected | none | none | Welch 2010 | Combined into one PA Memo (MILCON Verticals Stage 1) with P-305, P-306, P-307, P-310, P-326, P-802, and P-803. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period. PA Memo posted June 2021
J-012, J-302, (Previous) J-301 (New) | Consolidated HQ Facility (includes CLB-4 HQ, 3rd MEB CE, GCE Inf Bn HQ 1, GCE Inf Bn HQ 2, 4th Marines Reg HQ). | FY23 | No Historic Properties Affected | none | none | Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-018, J-023, J-032, J-034, J-036, J-037, and J-039. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
J-015 | Enlisted Dining Facility #1 (Original) Enlisted Dining Facility (New) | 2011 (Original) 2021 (New) | No Historic Properties Affected | none | none | Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-018, J-023, J-032, J-034, J-036, J-037, and J-039. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
J-030 Renamed J-033 | Base Enlisted Quarters - 1 Building | FY20 (JFY20) | No Historic Properties Affected | none | none | Welch 2010 | future project Planned for FY19. PA Memo for vertical construction to come next reporting period. PA Memo to include both J-016 and J-030 as renamed J-031 and J-033, respectively. 2019 update: initial vertical construction consultation was for J-031, J-033, P-459 (all are barracks), also P-311 and P-804. See comment on J-031 on line #18.
J-023 | Bachelor Officer Quarters 1 ‐ 3 (Previous) Bachelor Officer Quarters - 1 Building | 2013 (Original) FY21 | No Historic Properties Affected | none | none | Welch 2010 | Project was part of a multiple vertical construction project PA Memo submitted to SHPO on June 8, 2021.
J-018 | Security (Police) Station (Original) Security Building/Police Station (New) | 2012 (Original) FY22 (New) | No Historic Properties Affected | none | none | Welch 2010 | Project excpected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-023, J-032, J-034, J-036, J-037, J-038, J-039, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
J-008 | Fire Station | 2011 (Original) FY21 (New) | No Historic Properties Affected | none | none | Athens 2009 Welch 2010 | \Consultation completed upon signing of 2011 Military Relocation PA. Mitigation not required. Planning development. Project expected to be part of a multiple vertical construction project PA Memo in FY22. J-008 to be consulted on in future reporting period. Associated training area location to be determined (see J-008 I). Combined into one PA Memo (Mamizu Verticals Stage 1) with J-015, J-018, J-023, J-032, J-034, J-036, J-037, J-038, J-039, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
J-008 I (New) | Fire Fighting Training Area | 2024 (New) | No Historic Properties Affected | None | None | Pacheco et al 2020, Welch 2010 | PA memo deliverd 27 MAR 23, SHPO comments received 1 MAY 23, in resolution phase. Response submitted 17 JUL 23, confirmed complete 28 AUG 23.
Unassigned (Original) P-312 (New) | CRSP Warehouse, Phase 1 (Original) District Warehouse (New) | Unscheduled (Original) FY21 (New) | No Historic Properties Affected | none | none | Welch 2010 | Project was included in multiple vertical construction consultation (P-311, P-312, P-317, and P-804 Multiple Vertical Projects). PA Memo for design and construction submitted on 03/02/2021.
P-316 | Artillery Battery | FY24 | No Historic Properties Affected | none | none | Athens 2009, Pacheco et al. 2020 | PA memo for construction part of combined FY24 MILCON PA memo (P-316, P-406, P-408, P-760, P-870). Posted for review 8 AUG 23, SHOP comment received 5 SEP 23, response to comment 9 NOV 23.
P-610 | AAV/LAR/CEB Maint | 2029 (New) | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | future project at NBG Apra Harbor
J-032 | Bachelor Enlisted Quarters - 3 Buildings | FY21 | No Historic Properties Affected | none | none | Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-018, J-023, J-034, J-036, J-037, J-038, J-039, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021. Actual submittal included J-015, J-018, J-023, J-032, J034, J-036, J-037, and J-301. J-008 Separated out;
J-025 | Medical/Dental Clinic | FY21 | No Historic Properties Affected | none | none | Welch 2010 | Combined with J-011 (Mamizu vertical project) and PA Memo delivered on 2/17/2021. All projects within the J-001B project footprint have already been mitigated.
J-304 | Dental Co Admin | Beyond FY21 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | Project deleted
Unassigned (Original) P-317 (New) | 9th ESB Warehouse, Phase 1 (Original) Combined EOD Facility (New) | Unscheduled (Original) FY21 (New) | No Historic Properties Affected | none | none | Welch 2010 | Project was included in multiple vertical construction consultation (P-311, P-312, P-317, and P-804 Multiple Vertical Projects). PA Memo for design and construction submitted on 03/02/2021.
P-871U | Gas Chamber (Original) CBRNE Training (New) | FY23 (New) | No Historic Properties Affected | none | none | Haun 2008, Pacheco et al. 2020 | PA memo completed 11 SEP 23, no adverse effects
Unassigned (Original) J-401 (New) | Indoor Physical Fitness Center #2 (Original) Fitness Center (New) | Unscheduled (Original) Beyond FY22 ? (New) | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Welch 2010 | future project
J-033 | Bachelor Enlisted Quarters - 2 Buildings | 2020 (JFY 2019?) | No Historic Properties Affected | none | none | Pacheco et al. 2020, Welch 2010 | future project 2019 update: included in multiple vertical construction consultation; PA Memo delivered 7/8/19. Navy response to SHPO in progress. SHPO did not concur. Response to SHPO comments pending from Navy. Note name changes: J-016 became J031 andJ030 became J031. Both were included in multiple vertical property consultations that SHPO objected to. DON responded to SHPO objections on 6/16/20, addressing objections that referenced historic properties that had been, or were being data recovered.
J-034 | Bachelor Officer Quarters - 1 Building | 2022 | No Historic Properties Affected | none | none | Pacheco et al. 2020, Welch 2010 | Future project within J-001B. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-018, J-023, J-032, J-036, J-037, J-038, J-039, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
Unassigned (Original) J-402 (New) | Outdoor Playing Field | Unscheduled (Original) JFY23 (FY24) | No Historic Properties Affected | none | none | Pacheco et al. 2020, Welch 2010 | PA memo for construction part of combined FY24 MAMIZU PA memo (J-313, J-321, J-402, J-875). Posted for review 19 SEP 23, no comments, called complete 6 NOV 23.
Unassigned (Original) P-408 (New) | Religious Ministry Facility (Original) Religious Ministry Services (New) | Unscheduled (Original) FY25 (New) | No Historic Properties Affected | none | none | Pacheco et al. 2020, Welch 2010 | PA memo for construction part of combined FY24 MILCON PA memo (P-316, P-406, P-408, P-760, P-870). Posted for review 8 AUG 23, SHOP comment received 5 SEP 23, response to comment 9 NOV 23.
P‐606 (Original) J-313 (New) | Corrosion Control Facility (Original) Corrosion Control - Ground Phase 1 (New) | 2014 (Original) 2022 2024 (New) | No Historic Properties Affected | none | none | Athens 2009, Pacheco et al. 2020 | PA memo for construction part of combined FY24 MAMIZU PA memo (J-313, J-321, J-402, J-875). Posted for review 19 SEP 23, no comments, called complete 6 NOV 23.
Unassigned (Original) P-404 (New) | Exchange Auto Services (Original) Exchange Retail Store (New) | Unscheduled (Original) 2035 (New) | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Welch 2010 | future project
P-804 | Central Issue Facility | FY21 | No Historic Properties Affected | none | none | Welch 2010 | Project was included in multiple vertical construction consultation (P-311, P-312, P-317, and P-804 Multiple Vertical Projects). PA Memo for design and construction submitted on 03/02/2021.
J-875 | BSTF | FY24 | No Historic Properties Affected | none | none | Haun 1988, Pacheco et al. 2020 | PA memo for construction part of combined FY24 MAMIZU PA memo (J-313, J-321, J-402, J-875). Posted for review 19 SEP 23, no comments, called complete 6 NOV 23.
Unassigned (Original) P-407 (Previous) J-035 (New) | Library/Education Center/RMF (Original) Education Center (New) | Unscheduled (Original) Beyond FY22) 2023 | No Historic Properties Affected | none | none | Pacheco et al. 2020 Welch 2010 | Consultation was by a multiple vertical PA Memo that included J-014 Physical Training Complex; J-035 Education Center; J-318 Public Works/Maintenance Shops; J-323 Base Motor Pool
P-803 | Ind Combat Skills Trng | FY21 | No Historic Properties Affected | none | none | TBD | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (MILCON Verticals Stage 1) with P-305, P-306, P-307, P-310, P-326, P-802. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period. PA Memo posted June 2021
Unassigned (Original) P-802 (New) | Base DSSA Warehouse, Phase 2 (Original) Base Warehouse (New) | Unscheduled (Original) FY21 (New) | No Historic Properties Affected | none | none | Reinman 1977 Kurashina, McGrath and Manner 1987 Haun 1988 Highness and Haun 1990 Olmo, Mangieri, Welch and Dye 2000 Athens 2009 Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (MILCON Verticals Stage 1) with P-305, P-306, P-307, P-310, P-326, and P-803. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period. PA Memo posted June 2021
Unassigned (Original) P-760 | AV Simulation/MISTIC Training Facility (Original) Battle Sim Center (New) | Unscheduled (Original) FY24 (New) | No Historic Properties Affected | none | none | Haun 1988, Pacheco et al. 2020 | PA memo for construction part of combined FY24 MILCON PA memo (P-316, P-406, P-408, P-760, P-870). Posted for review 8 AUG 23, SHOP comment received 5 SEP 23, response to comment 9 NOV 23.
Unassigned (Original) P-410 (New) | Auditorium/Band Building (Original) Auditorium/Theater (New) | 2027 (New) | N/A | N/A | N/A | N/A | future project
Unassigned (Original) P-320 (New) | Recycling Center (Original) Recycle Center/Waste Transfer (New) | Unscheduled (Original) 2026 (New) | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Welch 2010 | future project
Unassigned (Original) P-406 (New) | Recreation Center | FY24 | No Historic Properties Affected | none | none | Pacheco et al. 2020 Welch 2010 | PA memo for construction part of combined FY24 MILCON PA memo (P-316, P-406, P-408, P-760, P-870). Posted for review 8 AUG 23, SHOP comment received 5 SEP 23, response to comment 9 NOV 23.
Unassigned (Original) P-414 (New) | Main Exchange (Original) Location Exchange (New) | Unscheduled (Original) Beyond FY22 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Welch 2010 | future project
Unassigned (Original) J-318 (New) | Public Works Facility (Original) Public Works/Maintenance Shops (New) | Unscheduled (Original) FY24 (New) | No Historic Properties Affected | none | none | Pacheco et al. 2020 Welch 2010 | Consultation was by a multiple vertical PA Memo that included J-014 Physical Training Complex; J-035 Education Center; J-318 Public Works/Maintenance Shops; J-323 Base Motor Pool
Unassigned (Original) P-409 (New) | Consolidated Club | Unscheduled (Original) Beyond FY22 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Welch 2010 | future project
Unassigned (Original) P-323 (New) Now J-323 | 5th ANGLICO Auto Shop (Original) Base Auto Shop (New) Base Motor Pool | Unscheduled (Original) Beyond FY22 FY 24 | No Historic Properties Affected | none | none | Welch 2010 | Consultation was by a multiple vertical PA Memo that included J-014 Physical Training Complex; J-035 Education Center; J-318 Public Works/Maintenance Shops; J-323 Base Motor Pool
P-321 now J-321 | Corrosion Control - Ground Phase 2 | FY24 | No Historic Properties Affected | none | none | Athens 2009, Pacheco et al. 2020 | PA memo for construction part of combined FY24 MAMIZU PA memo (J-313, J-321, J-402, J-875). Posted for review 19 SEP 23, no comments, called complete 6 NOV 23.
P-412 | Transient Quarters | Beyond FY22 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | future project
P-322 | Base EOD | Beyond FY22 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | future project
P-326 | PEI Warehouse | FY22 | No Historic Properties Affected | none | none | TBD | Future project. Future project within J001B APE. Combined into one PA Memo (MILCON Verticals Stage 1) with P-305, P-306, P-307, P-314, P-802, and P-803. PA Memo # 1 for combined MILCON Verticals (Stage 1) within the J-001B APE will be covered in the next reporting period. PA Memo posted June 2021
Unassigned (Original) P-324 (New) | 9th ESB Administration (Original) 9th ESB HQ (New) | Unscheduled (Original) FY24 (New) | No Historic Properties Affected | J-001B-002, J-001B-009, J-001B-010, J-001B-011, HR-12, HR-20, HR-22, HR-25 | none | Athens 2009, Dixon et al. 2018, Pacheco et al. 2020 Welch 2010 | Vertical project Combined with P309 and P325; PA Memo posted 2 FEB 2022, finalized 10 JUN 2022. Projects 324 and 325 may be impacted by decision on disposition of burials in Area D. P-324 not impacted by burials; the remaining work on them is being addressed by P-325.
P-459 | Bachelor Enlisted Quarters - 1 Building | FY20 (New) | No Historic Properties Affected | none | none | TBD | project was included in multiple vertical construction consultation; PA Memo delivered 7/8/19. SHPO objected to determination. DON responded to SHPO objections on 6/16/20, addressing objections that referenced historic properties that had been, or were being data recovered.
P-405 | Bachelor Officer Quarters | Beyond FY21 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | future project
J‐021 (Original) P-413 (New) | Temporary Lodging Facility | Unscheduled (Original) 2027 (New) | No Historic Properties Affected | none | none | Welch 2010 | Project was consulted on by AAFB; SHPO concurred with determination of no historic properties affected. Future FY27 project. Current schedule shows Design PA Memo in FY25.
Unassigned (Original) P-325 (New) | 9th ESB Warehouse, Phase 2 (Original) 9th ESB EOD (-) (New) | Unscheduled (Original) FY 24 (New) | No Adverse Effect | J-001B-002, J-001B-009, J-001B-010, J-001B-011, HR-6, HR-9, HR-11, HR-12, HR-13, HR-14, HR-16, HR-19, HR-20, HR-21, HR-22, HR-24, HR-25 | None | Dixon et al. 2018, Pacheco et al. 2020, Welch 2010 | Vertical project Combined with P309 and P324; PA Memo posted 2 FEB 2022, finalized 10 JUN 2022. Projects 324 and 325 may be impacted by decision on disposition of burials in Area D. PA memo for construction planned for Q1 FY24, optional project work includes landscaping around the Area D burials. PA memo for construction was completed in June 2024.
J-036 | Bachelor Enlisted Quarters | 2021 | No Historic Properties Affected | none | none | Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-018, J-023, J-032, J-034, J-037, J-038, J-039, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
J-037 | Bachelor Enlisted Quarters | 2021 | No Historic Properties Affected | none | none | Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-018, J-023, J-032, J-034, J-036, J-038, J-039, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
J-038 | Bachelor Enlisted Quarters | 2021 | No Historic Properties Affected | none | none | Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-018, J-023, J-032, J-034, J-036, J-037, J-039, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
J-039 | Bachelor Enlisted Quarters | 2021 | No Historic Properties Affected | none | none | Welch 2010 | Project expected to be part of a multiple vertical construction project PA Memo in FY21. Combined into one PA Memo (Mamizu Verticals Stage 1) with J-008, J-015, J-023, J-032, J-034, J-036, J-037, J-038, and J-301. PA Memo # 1 for combined Mamizu Verticals (Stage 1) within the J-001B APE was submitted to SHPO on June 8, 2021.
P-870 | Engineering Pit (Dig Pit) (Original) Eng & Brdg Cmplx (New) | FY24 | No Historic Properties Affected | none | none | Pacheco et al 2020, Welch 2010 | PA memo for construction part of combined FY24 MILCON PA memo (P-316, P-406, P-408, P-760, P-870). Posted for review 8 AUG 23, SHOP comment received 5 SEP 23, response to comment 9 NOV 23.
Naval Base Guam - Naval Munitions Site
P-608 | ECMs (NBGOA) | FY25 | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | Further Consultation Required via PA Memo Process | TBD | Future project 2019 update: PA Memo delivered 6/7/19; SHPO advised DON of documented site in APE. Additional research, including a site visit discovered standing latte set adjacent to proposed APE. Additional survey of the area is planned. Geotech work is being monitored. UPDATE: Alternate area for project is being surveyed, also considering option of shifting project south within preferred location to avoid Fena Lake site. UPDATE: Fieldwork (survey with subsurface testing) was completed in Kitts Road alternative on 6/17/20. End of Fieldwork report was delivered to SHPO for review on 6/23/2020. Addendum Archaeological Surface and Subsurface Survey Plan (Parsons Road) submitted to SHPO on 8/31/20. SHPO provided comments on the work plan on 2/19/21. End of fieldwork letter report for Parsons Road extension and South Kitts Road extension delivered to SHPO on 2/19/21. Draft results of archaeological surface and subsurface survey in preparation as of this reporting period. Draft report for Parsons Road survey delivered July 14, 2021 Report finalized November 2021. PA memo for design fiedl studie planned for FY23. Project was moved to Parsons Road location to avoid impacts to archaeological sites near Fena Reservoir (Kitts Road location). While survey found no historic properties in this APE, the boundary of a scatter of abandoned magazines extends into the eastern side of the APE. The scatter is eligible but might be covered by a Program Comment. Of greater concern, there are wetland concerns in portions of the APE. Those concerns must be considered, possibly by avoidance by design and/or additional CR and NR surveys to shift the APE westward. Revised PA memo for Parsons Road location transmitted 15 JUNE 2023, in SHPO and public review period.no comments received, complete 7 AUG 23. Revised PA Memo for Design (due to changes in APE after June 2023) FY24 Q2. Revised PA Memo needed for additional geotech work associated with the utilities at Orote and Naval Mag. Revised PA memo for design completed in June 2024.

## Miscellaneous
Project Number | Project Title | FY Execution | DoD Effect Determination | Historic Properties Directly Affected | Historic Properties Indirectly Affected | FEIS/Original Survey Reference | Status: Current as of December 2024
Miscellaneous
Unassigned | Tumon-Maui Well Rehabilitation (New) RC2016-0122 | 2011 | No Adverse Effect | 66-01-2278 | None | Yoklavich, Craib and Drolet 1996 | Consultation complete. No Adverse Effect determination due to compliance with Secretary of Interior Standards for Rehabilitation.
Unassigned | Ungulate (Hoofed Animal) Fencing (New) RC2012-9846 | 2011 | No Historic Properties Affected | N/A | N/A | Reinman and Nees 1998 Dixon, Gosser, Gilda and Nees 2004 Welch 2010 | Consultation complete. This was along Rt. 2 from NBG main gate south to join existing fence across from Apra Heights Mobil Station.
Unassigned | Wetland Restoration, Phase 1 (New) RC2011-8981 | 2011 | No Adverse Effect | N/A | N/A | Dixon, Gosser, Gilda and Nees 2004 | Consultation Complete
Unassigned (Original) P-102 (New) | Underground Power Line (Original) Power Upgrade - Harmon to NCTS SS UG (New) RC2015-0129 | Unscheduled (Original) 2017 (New) | No Historic Properties Affected | none | none | Welch 2010 | future project; Sec 106 Consultation complete RC2015-0129, dated Oct 28, 2015. Changes due to ongoing P-102 design (route change at AAFB) requires further consultation (PA Memo #1 Revision was delivered to SHPO April 2017 with SHPO response condurring with "no historic properties affected"). Consultations completed. January 2018 - contractor found proposed laydown area unsuitable due to tendancy to flooding after rain; proposed an alternate area already permitted and in use about 1/2 mile south of originally proposed area. Revised PA Memo is in preparation for SHPO review. Revision concurred on by SHPO.
Unassigned (New) P-103 (Original) | Water Wells/Pipeline RC2016-0122 | Unscheduled (Original) 2022 (New) | Further Consultation Required via PA Memo Process no adverse effect determination regarding testing phase. PA Memo process completed for construction phase in 2020 with responses to Senators' comments. | Further Consultation Required via PA Memo Process none affected by testing phase. PA Memo process completed for construction phase in 2020 with responses to Senators' comments. | Further Consultation Required via PA Memo Process none affected by testing phase. PA Memo process completed for construction phase in 2020 with responses to Senators' comments. | Welch 2010 | 2017: Project Design has changed in response to need to work outside of explosive safety arcs established around AAFB munitions storage bunkers. New design eliminates proposed eastern wells and corridors. Revised PA Memo will be submitted for SHPO review. Revised PAM 1 delivered to SHPO July 31, 2017; SHPO comments dated Sept. 11, 2017 stated disagreement with DON eligibility assessment for site that revised corridor passes through. MCAG and AAFB archaeologists visited the location in question on 12/4/17 and reported physical separation of sites in question and confirmed original determination of not eligible for the site the corridor passes through. DON responded to SHPO comments on 1/17/18. PAM 2 was delivered to SHPO on 2/15/2018 with comments due 3/26/18. 2019: Although design work ongoing, more revisions to construction footprint anticipated due to site constraints due to USGS Geomagnetism Laboratory instrumentation. 2019: PAM2 for construction was delivered to SHPO 8/23/2019. Details of corridor near eligible sites were included to demonstrate separation. Additional consultation needed to address design changes. UPDATE: Submitted Archaeological Monitoring and Discovery Plan to SHPO on 12/9/20. No comments recieved. As of the current reporting period Jan-Jun 2022, construction is in progress with archaeological monitoring per the 2018 resolution agreement. Bone fragments were discovered and were treated as human remains (HR-1) per the HR protocol as a precaution; ultimately the remains were determined to be non-human.
P-104 | Water Well Field II | FY26 | TBD | TBD | TBD | TBD | Future project currently planned to be within P-103 APE to install additional wells that were options to the P-103 scope of work.
P-416 | High School - Expand | 2026 (New) | TBD | TBD | TBD | TBD | future project
J-200-II | North Ramp Utilities Communication Lines AAFB (IT/Comm Phase 1) (RC2020-0702) | 2024 (New) | No Historic Properties Affected | None | None | Aaron et al, 2007; Athens 2009; Church et al. 2009; Davis 1983; DeFant and Guerrero 2006; Dixon and Walker 2011; Dixon et al 2011; Dixon et al. 2014a; Dixon et al 2014B; Dixon 2015; Grant et al 2007; Haun 1988; Haun 1989; Hlatky and Maxwell 2018; Hokanson et al 2007; Hunter-Anderson and Moore 2003; Kurashina et al 1986; Liston 1996; Mason Architects 2004; Mohlman 2015; Welch 2010; Yee 2004 | future project to be presented as J-200 Phase 2. PA Memo # 1 delivered June 18, 2020; no comments received from SHPO. Revised PA Memo # 1 was delivered on 11/17/2020; the totoal APE decreased from 36.9 to 35.9 hectares. SHPO non-concurrence on 1/19/2021. NFM responded to each SHPO comment on 7/29/21. Construction PA Memo currently on hold due to alignment discrepancy.Construction PA Memo work to resume in January 2024. Construction anticipated for 22 May 24, however, will likely delay. Hold on construction lifted, Construction PA memo forthcoming
P-745 | Relocation of US F&W Facilities outside of SDZ at Ritidian | 2026 (New) | Further Consultation Required via PA Memo Process for construction | Further Consultation Required via PA Memo Process for construction | Further Consultation Required via PA Memo Process for construction | Bayman et al. 2010; Carson (multiple reports); Carson et al. 2014; Department of Interior 1993; Dixon et al. 2017; Dixon and Schaefer 2014; Jalandoni et al. 2012, Church 2009, Dixon 2014, Dixon et al. (2011, 2012), Kurashina et al. 1987, Welch 2010 | Project will relocate US F&W facilities to a location outside of the Surface Danger Zone of the firing ranges on the plateau, as required under an inter-agency Memorandum of Agreement. Planning archaeological surveys were conducted in consultation with SHPO. Project added. PA memo for design studies completed, no adverse effects. PA Memo for Construction anticipated for FY25, Q4 construction award
P-187 | Brown Tree Snake Exclusion Barrier - Design Studies | FY23 | No Historic Properties Affected | none | none | Welch 2010; Pacheco et al. 2020 | P-187 memo for construction-submitted for SHPO and public review 12 MAY 23, comments due 26 JUN 23. No SHPO or public comments received, called complete 27 June. SHPO comments received 14 AUG 23, considered advisory, responded 24 AUG 23, NFA. One area discovered during monitoring. Further work being scheduled. Human remains recovery field work at HR1 was completed.
Unassigned | IT/Comm Phase 2 | Beyond FY20 | TBD | TBD | TBD | TBD | future project

## Newly Added
Project Number | Project Title | FY Execution | DoD Effect Determination | Historic Properties Directly Affected | Historic Properties Indirectly Affected | FEIS/Original Survey Reference | Status: Current as of December 2024
Miscellaneous
H-435 | Tumon-Maui Well Rehabilitation (New) RC2016-0122 | 2026 |  |  |  |  | Project Cancelled
P-104 | Water Wells | 2026 |  |  |  |  | Moved to Miscellaneous (Row 8)
P-330 | Exploitation Facility | 2028 |  |  |  |  | Moved to Marine Corps Base Guam - Urban Training Complex (formerly Andersen South) (Row 37)
P-504 | Maintenance Building | 2028 |  |  |  |  | Project Cancelled
P-503 | Supply Building | 2029 |  |  |  |  | Project Cancelled
P-507 | Engineering Building Annex | 2030 |  |  |  |  | Project Cancelled
P-509 | Medical Admin Building | 2030 |  |  |  |  | Project Cancelled
P-501 | Logistics Building I | 2032 |  |  |  |  | Project Cancelled
P-506 | Logistics Building III | 2032 |  |  |  |  | Project Cancelled
P-555 | Paraloft | 2033 |  |  |  |  | Project Cancelled
P-505 | Logistics HQ Building | 2033 |  |  |  |  | Project Cancelled
P-508 | Communications Building | 2034 |  |  |  |  | Project Cancelled
P-554 | Aircraft Control Building | 2034 |  |  |  |  | Project Cancelled
P-553 | Aircraft Communications Building | 2034 |  |  |  |  | Project Cancelled
P-419 | Club and Restaurant | 2035 |  |  |  |  | Project Cancelled
P-541 | Child Development Center II | 2035 |  |  |  |  | Project Cancelled
P-542 | Youth Center II | 2035 |  |  |  |  | Project Cancelled
P-510 | Dining Facility Annex | 2036 |  |  |  |  | Project Cancelled
P-511 | Armory #2 | 2036 |  |  |  |  | Project Cancelled
P-512 | BEQ | 2036 |  |  |  |  | Project Cancelled
P-543 | Location Exchange/Bowling/Food Court | 2036 |  |  |  |  | Project Cancelled
P-513 | BEQ/BOQ | 2037 |  |  |  |  | Project Cancelled
P-544 | Aquatics Facility | 2037 |  |  |  |  | Project Cancelled
H-1 | Family Housing Phase A | 2028 |  |  |  |  | Project Cancelled
H-2 | Family Housing Phase B | 2029 |  |  |  |  | Project Cancelled
H-3 | Family Housing Phase C | 2031 |  |  |  |  | Project Cancelled
H-4 | Family Housing Phase D | 2032 |  |  |  |  | Project Cancelled
H-5 | Family Housing Phase E | 2033 |  |  |  |  | Project Cancelled
D-1 | DODEA | 2028 |  |  |  |  | Project Cancelled
D-2 | DODEA | 2029 |  |  |  |  | Project Cancelled
D-3 | DODEA | 2030 |  |  |  |  | Project Cancelled
D-4 | DODEA | 2031 |  |  |  |  | Project Cancelled
D-5 | DODEA | 2032 |  |  |  |  | Project Cancelled
D-6 | DODEA | 2033 |  |  |  |  | Project Cancelled
D-7 | DODEA | 2034 |  |  |  |  | Project Cancelled