## PAC Workload Projections PPv5
NAVFAC PACIFIC WORKLOAD PROJECTIONS AS OF 31 MARCH 2024
The list of projects, design, and construction tools are to increase your awareness of opportunities at NAVFAC PACIFIC. If you are interested in any of the items listed, please visit www.SAM.gov. Location may not reflect actual physical location of project. Confirm project location in project synopsis once issued. For Design Agent, IH = NAVFAC PACIFIC and AE = Architect/Engineer Consultant DISCLAIMER: Information contained herein is not a guarantee of the Government's course of action concerning current or future requirements. The information presented reflects current Government intentions; but is subject to change. Published solicitations, if issued, are the only documents that should be relied upon in determining the Government's actual requirements.
Proj # | Project Title | Location Area of Responsibility | Design Agent | Acquistion Tool 1 | Design Level 1 | Potential Award Value | Proposed RFP | Proposed Award | Proposed Award1 | Proposed RFP1
10 | EXTEND RUNWAY (YAP) | NAVBASE GUAM | AE | MACC | Design Bid Build | $100M - $250M | FY25 Q1 | FY25 Q4 | Complete-Issued | Complete-Issued
12 | NORTH AIRCRAFT PARKING RAMP | US NAVSUPACT ANDERSEN GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $250M - $500M | FY25 Q1 | FY25 Q4
20 | AIRCRAFT PARKING APRON (YAP) | NAVBASE GUAM | AE | MACC | Design Bid Build | $100M - $250M | FY25 Q1 | FY25 Q4
30 | PERIMETER ROAD (YAP) | NAVBASE GUAM | AE | MACC | Design Bid Build | < $25M | FY24 Q4 | FY25 Q2
325 | PDI: 9TH ESB EQUIPMENT AND MAINTENANCE FACILITY | US NAVSUPPACT MCB GUAM | AE | MACC | Design Bid Build | $100M - $250M | FY24 Q3 | FY24 Q4 | Complete-Issued | Complete-Issued
408 | PDI: RELIGIOUS MINISTRY SERVICES FACILITY | US NAVSUPPACT MCB GUAM | IH | MACC | Design Bid Build | $25M - $100M | FY25 Q1 | FY25 Q3
541 | MISSILE INTEGRATION TEST FACILITY | NAVBASE GUAM | AE | MACC | Design Bid Build | $100M - $250M | FY24 Q2 | FY24 Q4
608 | PDI: EARTH COVERED MAGAZINES | NAVBASE GUAM | AE | MACC | Design Bid Build | $100M - $250M | FY24 Q4 | FY25 Q2
614 | PDI: JOINT CONSOLIDATED COMMUNICATIONS CENTER | US NAVSUPACT ANDERSEN GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $250M - $500M | FY25 Q2 | FY25 Q4
649 | JOINT COMMUNICATIONS UPGRADE (INC) | NAVBASE GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $250M - $500M | FY24 Q2 | FY24 Q4 | FY24 Q4
693 | PDI: GUAM DEFENSE SYSTEM, COMMAND CENTER | US NAVSUPACT ANDERSEN GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $100M - $250M | FY25 Q1 | FY25 Q4
694 | PDI: GUAM DEFENSE SYSTEM, ENHANCED INTEGRATED AIR AND MISSILE DEFENSE (EIAMD) | US NAVSUPACT ANDERSEN GUAM | AE | MACC | Design Bid Build | $250M - $500M | FY25 Q2 | FY25 Q4
760 | PDI: TRAINING CENTER | US NAVSUPPACT MCB GUAM | AE | MACC | Design Bid Build | $25M - $100M | FY24 Q3 | FY24 Q4
0800 | MULTIPURPOSE HANGAR (TINDAL, AUS) | US NAVSUPPACT MCB GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $25M - $100M | FY24 Q4 | FY25 Q2
870 | PDI: 9TH ESB TRAINING COMPLEX | US NAVSUPPACT MCB GUAM | AE | Stand Alone Construction Contract | Design Bid Build | < $25M | FY24 Q2 | FY24 Q4
923 | PDI: AIRCRAFT PARKING APRON | MCB HAWAII KANEOHE | AE | Stand Alone Construction Contract | Design Bid Build | $25M - $100M | Complete-Issued | FY24 Q4
941 | PDI: MAINTENANCE SUPPORT FACS - RAAF DARWIN | MCB HAWAII KANEOHE | AE | Stand Alone Construction Contract | Design Bid Build | $25M - $100M | Complete-Issued | FY25 Q2
949 | PDI: AIRCRAFT MAINTENANCE HANGAR - RAAF DARWIN | MCB HAWAII KANEOHE | AE | Stand Alone Construction Contract | Design Bid Build | $100M - $250M | Complete-Issued | FY25 Q2
1001 | AERIAL PORT FACILITY | US NAVSUPACT ANDERSEN GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $25M - $100M | FY25 Q1 | FY25 Q3
2301 | HSC-25 Complex | US NAVSUPPACT ANDERSEN GUAM | AE | MACC | Design Build | $500M - $1B | FY24 Q4 | FY25 Q2
6002 | RSAF NON-HARDENED HANGAR | US NAVSUPACT ANDERSEN GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $100M - $250M | FY25 Q1 | FY25 Q4
6003 | RSAF PUMP HOUSE AND FUEL STORAGE | US NAVSUPACT ANDERSEN GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $100M - $250M | FY25 Q1 | FY25 Q4 | Complete-Issued | Complete-Issued
9001 | TRANSIENT AIRCRAFT PARKING APRON | NAVBASE GUAM | AE | Stand Alone Construction Contract | Design Bid Build | $25M - $100M | FY24 Q2 | FY24 Q3
H308 | REPLACE ANDERSEN HOUSING PH IX | US NAVSUPACT ANDERSEN GUAM | IH | Stand Alone Construction Contract | Design Build | $250M - $500M | FY24 Q4 | FY25 Q4
H434 | REPLACE ANDERSEN HOUSING PH X | US NAVSUPACT ANDERSEN GUAM | IH | Stand Alone Construction Contract | Design Build | $25M - $100M | FY24 Q4 | FY25 Q4
J017-V | GOJ MCBCB TO NCTS POTABLE WATERLINE INTERCONNECT | US NAVSUPPACT MCB GUAM | AE | MACC | Design Bid Build | $25M - $100M | FY24 Q4 | FY25 Q2 | FY22 Q4 | FY22 Q4
J318 | GOJ - PUBLIC WORKS / MAINTENANCE SHOPS | NAVBASE GUAM | AE | MACC | Design Bid Build | $100M - $250M | Complete-Issued | FY24 Q4
J321 | GOJ - CORROSION CONTROL - GRND PH 2 | US NAVSUPPACT MCB GUAM | AE | MACC | Design Bid Build | $25M - $100M | FY24 Q3 | FY24 Q4
J323 | GOJ - BASE MOTOR POOL | NAVBASE GUAM | IH | MACC | Design Bid Build | $25M - $100M | Complete-Issued | FY24 Q4
J875 | GOJ - BSTF | US NAVSUPPACT MCB GUAM | AE | MACC | Design Bid Build | $100M - $250M | FY24 Q3 | FY25 Q1