## Contractor
PWD/SDMPO/ FEAD/ROICC | High Risk Activities | Specific Project and Contract No. | Specific Risk | Contractor and POC | Date Leader's brief completed | Date JHA associated training completed by workers | Severity | Probablity | RAC | Estimated start & completion | Comments (Navy oversight, 5-steps of ORM, etc) | "New" or "Continuing" construction
FEAD NWS Seal Beach | Demolition/ Rock Salvage & Placement, Fill Operations, Soils Compaction Testing- Nuclear Gauge (High/Heavy) (Landside) | N62473-19-C-2450 P-224 Causeway, Boat Channel & Turning Basin: - Earthwork, Excavation - for, Roads, Truck Turn-around, Moles | 1. Crushing/caught between/equipment, struck by 2. Fall in ocean- equipment/personnel 3. Severe Weather - sea state, rain storms, wind, lightning 4. Exposure to radioactive material. | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 2021-08-23 | 2020-01-14 | I : Catostrphic | C: Occasional | 3: MODERATE / MODERATE RISK (M) | 2-22-2022 - 10-2022 | 1a. Workers shall stand away from vehicles being loaded or unloaded to avoid being struck by spillage or falling materials. 1b. Ensure that operators unloading equipment are aware of their surrounding. Laborers working around equipment must visual contact with operator. 1c. Workers shall not get between the load and the ground,equipment or materials while being hoisted. 1d. All equipment will have audible back-up alarms/devices. 2a. Safeguards such as barriers, curbs, or other structures shall be provided to prevent heavy operating equipment and personnel from falling into the ocean. 2b. USCG approved PFD shall be worn by personnel regardless of other safety devices used. 2c. A Safety Skiff or equivalent rescue vessel shall be readily available throughout the duration of these activities. 2d. All Heavy Operating Equipment will have a Glass Breaking Device in cabin. 3a. During severe weather (hi-surf, rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Sea state of 6-ft swells/surf, Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. 4. Contractor forward Submital package for XRF Operations and must be approved by FEAD-COT prior to bringing equipment on base for inspection via Contractor XRF Oversight Checklist. Operator must follow all items of Checklist during operations. | Continuing
FEAD NWS Seal Beach | Rock / Fill Placement & Lifting bulldozer from barge to barge, w/ Floating Derrick Crane (High/Heavy) (DBLA - Floating Derrick Crane) | N62473-19-C-2450 P-224 Causeway, Boat Channel & Turning Basin -Fill Material Placement for new Pier -Fill to establish Toe & Slope at, W. Mole Breakwater | 1. Dropping loads 2. Crushing caught in between heavy equipment, derricks, barges, skiffs 3. Fall in ocean- equipment/personnel 4. Severe Weather - sea state, rain storms, wind, lightning | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 2021-08-23 | 2020-01-03 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 8-13-2022 to 10-30-2022 | 1a. NAVFAC Crane Inspectors will inspect Crane and Rigging prior to Crane Operations and every 30 days as required thereafter. 2a. Workers shall stand away from vehicles being loaded or unloaded. 2b. Ensure operators are aware of their surrounding. Laborers working around equipment must be have visual and radio contact with operator. 2c. Workers shall not get between the load and the ground,equipment or materials while being hoisted. 2d.Set up swing circle to ensure no personnel enter area while load is suspended. 2e. Powered mobile equipment shall have audible warning devices. 3a. Safeguards such as barriers, curbs, or other structures shall be provided to prevent operating equipment from falling into the ocean. 3b. USCG approved PFD shall be worn by personnel regardless of other safety devices used. 3c. A Safety Skiff or equivalent rescue vessel shall be readily available throughout the duration of these activities 4a. During severe weather (hi-surf, rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Sea state of 6-ft swells/surf, Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Pile Driving Operations (Valkyrie) -Floating Derrick- Pile Driver) | N62473-19-C-2450 P-224 Causeway, Boat Channel & Turning Basin: -Dolphin Cat-Walks Pile Driving - Falsework support | 0. Crane compliance 1- Hammer disengagement 2. Crushing/caught inbetween/Leads/equipment, derricks-barges, skiffs 3. Fall in ocean- equipment/personnel 4. Severe Weather - heavy seas/wind | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 44448 | 44449 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | Onsite 7-11-2022 to 9-10-2022 Dolphin Piles | 0. NAVFAC Crane Oversight Inspectors will inspect Crane and Rigging prior to Crane Operations and every 30 days as required thereafter. 1a. Ensure Pile driving equipment is outfitted with a positive and negative restraint device to prevent accidental hammer disengagement i.e., preventing the hammer from falling or uncontrolled rising out of the lead. 1b. Conduct Daily Inspection of Pile Driving equipment to include the hammer, cushion blocks, rigging, fuel lines, pressurized hoses, clamps, welds, hardware, and all other pile driving associated equipment. 2a. All employees shall be kept clear when piling is being hoisted into the leads. 2b. Employees shall be prohibited from remaining on leads or ladders while the pile is being driven.--Workers shall stand away from equipment being loaded or unloaded. 2c. Ensure operators are aware of their surrounding. Laborers working around equipment must be in visual and radio contact with operator. 2d. Workers shall not get between the load and the ground,equipment or materials while being hoisted. 2e.Set up swing circle to ensure no personnel enter area while load is suspended. 2f. Hoisting and driving of piling shall be done by use of a closed shackle or other positive attachment that will prevent accidental disengagement of the rigging. 3a. Safeguards such as barriers, curbs, or other structures shall be provided to prevent operating equipment from falling into the ocean. 3b. USCG approved PFD shall be worn by personnel regardless of other safety devices used. 3c. A Safety Skiff or equivalent rescue vessel shall be readily available throughout the duration of these activities 4a. During severe weather (hi-surf, rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Sea state of 6-ft swells/surf, Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | False-work (High/Heavy) (VULCAN) - Floating Derrick Crane) | N62473-19-C-2450 P-224/226 Causeway, Boat Channel & Turning Basin Load and off-load false-work, beams from trucks and barges, support False Work Operations. | 1. Dropping loads 2. Crushing caught in between heavy equipment, derricks, barges, skiffs 3. Fall in ocean- equipment/personnel 4. Severe Weather - sea state, rain storms, wind, lightning | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 2021-08-23 | 2021-12-03 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 12/3/2021 - 12/30/2022 | 1a. NAVFAC Crane Inspectors will inspect Crane and Rigging prior to Crane Operations and every 30 days as required thereafter. 2a. Workers shall stand away from vehicles being loaded or unloaded. 2b. Ensure operators are aware of their surrounding. Laborers working around equipment must be have visual and radio contact with operator. 2c. Workers shall not get between the load and the ground,equipment or materials while being hoisted. 2d.Set up swing circle to ensure no personnel enter area while load is suspended. 2e. Powered mobile equipment shall have audible warning devices. 2f. Keep walking areas clear of debris avoiding slips, trips, falls. 3a. Safeguards such as barriers, curbs, or other structures shall be provided to prevent operating equipment from falling into the ocean. 3b. USCG approved PFD shall be worn by personnel regardless of other safety devices used. 3c. A Safety Skiff or equivalent rescue vessel shall be readily available throughout the duration of these activities 4a. During severe weather (hi-surf, rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Sea state of 6-ft swells/surf, Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Setting Tension Bands, Horse Collars, Slab Beams, Wedge Packs, Soffit Panels, Glulams, | N62473-19-C-2450 P-224 Causeway, Boat Channel & Turning Basin: FALSEWORK - FORMWORK | 1. Dropping loads 2. Crushing/caught between/equipment 3. Fall in water 4. Severe Weather | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 2022-02-28 | 2022-02-28 | I : Catostrphic | C: Occasional | 3: MODERATE / MODERATE RISK (M) | 2/28/2022 - 12/2022 | 1a. NAVFAC Crane Inspectors will inspect Crane and Rigging prior to Crane Operations and every 30 days as required thereafter. 1b. Proper hand signals shall be used by rigger. 1c.Tag lines shall be used to control all loads. 2a.Clear all potential tripping hazards glove and arm guards will be worn for cuts and Lacerations 2b. Ensure operators are aware of their surroundings. Laborers working around equipment must have visual contact with operator. 2c. Workers shall not get between the load and the ground, equipment or materials while being hoisted. 2d.Set up swing circle to ensure no personnel enter area while load is suspended. 3a. All workers will wear Personal Floatation Devices (PFD). 3b. A Skiff will be in water in case worker/s fall in water. Work floats will be included. 4a. During severe weather (rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Reinforcing Steel | N62473-19-C-2450 P-224 Causeway, Boat Channel & Turning Basin: | 1. Dropping load 2. Crushing/caught between/equipment 3. Severe Weather | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 2022-05-02 | 2022-05-02 | I : Catostrphic | C: Occasional | 3: MODERATE / MODERATE RISK (M) | 5/5/2022 -1-2023 | 1a.Proper hand signals shall be used by rigger. 2a.Tag lines shall be used to control all loads. 2b. All equipment will have audible back-up alarmes/devices. 2c.Check Boom lift operator certifications 2d. Reach Lift shall have an initial inspection and certified by the Navy Crane Committees prior to operation and a daily inspection thereafter. 2e.Rebar shall be secured (tied) properly to prevent rolling out while walking. 3a.Stretching prior to carrying loads / Handle workable loads / Clear all potential tripping hazards Glove and Arm Guards will be worn for cuts and Lacerations | Continuing
FEAD NWS Seal Beach | Concrete Construction | N62473-19-C-2450 P-224 Causeway, Boat Channel & Turning Basin: | 1.Crushing/caught between/equipment 2. Concrete spatter in eyes 3. Concrete exposure on hands/skin 4.Severe Weather | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 2022-05-02 | 2022-05-02 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 5/5/2022 -1-2023 | 1a. Ensure work site is safed off with barracades / signs. 1b. Workers shall stand away from Conctete Mixer trucks and Concrete Boom Trucks 1c. Ensure that equipment operators loading / unloading are aware of their surroundings. 1d. Laborers working around equipment must be in visual contact with operator. 1e. All equipment will have audible back-up alarmes/devices. 2a. All workers will wear ANZI rated safety glasses at all times. 2b. Workers will wear required PPE gloves for concrete work. 3a. During severe weather (rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Earthwork / Excavations Trenching , Underground Utilities | N62473-19-C-2450 P-224 Causeway, Boat Channel & Turning Basin: Excavations | 1. Caught inbetween equipment/crushed 2. Cave-ins 3. Weather, wind Severe Weather | Manson/Connolly SB JV SSHO-Pete Hernadez 562-477-0132 Super -Christopher Eagle 949-232-7887 | 2021-12-06 | 2021-12-06 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 2-2022 to 12-2022 | 1a. Workers shall stand away from vehicles being loaded or unloaded to avoid being struck by spillage or falling materials. 1b. Ensure that operators are aware of their surroundings.Laborers working around equipment must be in positive contact with operator and wearing required PPE. 1c. All equipment will have audible back-up alarmes/devices. 2a. Excavated materials shall be placed at least 2-ft from edge of excavation. 2b. Protection (barracades) shall be provided to prevent personnel, vehicles and equipment from falling into excavations. 2c. Trenches will have means of egrees-ladders / benching / sloping, as required. 2d. Trenches will be inspected daily by the competent person for conditions that could cause cave-ins or other unsafe conditions. 3a. During severe weather (rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Earthwork / Excavations/Surcharrge Piles | P243 MISSILE MAGAZINES | 1. Caught inbetween equipment/crushed 2. Cave-ins 3. Weather, wind Severe Weather | Reyes Construction Inc. SSHO- Ron Larson 909-837-8860 QCM- Steven Arteaga 909-762-2243 | 44474 | 44474 | II: Critical | D: Seldom | 3: MODERATE / MODERATE RISK (M) | 10/04/2021 - 02/25/2023 | 1a. Workers shall stand away from vehicles being loaded or unloaded to avoid being struck by spillage or falling materials. 1b. Ensure that operators are aware of their surroundings.Laborers working around equipment must be in positive contact with operator and wearing required PPE. 1c. All equipment will have audible back-up alarmes/devices. 2a. Excavated materials shall be placed at least 2-ft from edge of excavation. 2b. Protection (barracades) shall be provided to prevent personnel, vehicles and equipment from falling into excavations. 2c. Trenches will have means of egrees-ladders / benching / sloping. 2d. Trenches will be inspected daily by the competent person for conditions that could cause cave-ins or other unsafe conditions. 3a. During severe weather (rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Install Mechanincal/Electrical/Plumbing | B907 HVAC/Lighting Retrofit-UESC | Electrical shock Fall From Heights/Tip Over/Personnel Injury | SoCal Gas Co Evenings-Pride Metcalf 562-922-3694 Days- Miachael Kung 562-370-6938 | 44473 | 44462 | II: Critical | D: Seldom | 3: MODERATE / MODERATE RISK (M) | 4/19/21-10/31/2022 | Construction is complete on this project. Leaving this as continuing in the event that the KTR needs to perform any physical changes or repairs to the system. Lock-out, Tag-out: Both locks and tags are required. Check ground conditions. Ensure enough room to move safely around personnel, equipment, tools and materials. When possible position lift parallel to the deck edge. If perpendicular a stop/chock must be used if within 8in of a leading edge. Lifts must not be closer than 3 feet from each other. | Continuing
FEAD NWS Seal Beach | Crane Lift (Non Critical) Install Fiber poles | Northside Fiber Project | 1. Dropping load 2. Crushing/caught between/equipment 3a. Severe Weather | Barkley Andross Corp SSHO- Bryan Smithwick 760-244-4311 QC- Tye Andross 760-963-4751 | 2021-12-02 | 2021-12-02 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 02Dec21-03Jan22 | 1a. NAVFAC Crane Inspectors will inspect Crane and Rigging prior to Crane Operations and every 30 days as required thereafter. 2a. Workers shall stand away from vehicles being loaded or unloaded. 2b. Ensure operators are aware of their surrounding. Laborers working around equipment must have visual contact with operator. 2c. Workers shall not get between the load and the ground,equipment or materials while being hoisted. 2d.Set up swing circle to ensure no personnel enter area while load is suspended. 2e. Powered mobile equipment shall have audible warning devices. 3a. During severe weather (rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment.Winds 25 mph+- or as deemed unsafe, Lightning 10 miles away or less, Rain deemed unsafe slipperu wet unsafe exposure. | Continuing
FEAD NWS Seal Beach | Earthwork/ Excavations under 5-ft Comm/Electrical Fiber Pole Installation | Northside Fiber Project | 1. Caught inbetween equipment/crushed 2. Cave-ins 3. Weather, wind Severe Weather | Barkley Andross Corp SSHO- Bryan Smithwick 760-244-4311 QC- Tye Andross 760-963-4751 | 2021-12-02 | 2021-12-02 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 02Dec21-03Jan22 | 1a. Workers shall stand away from vehicles being loaded or unloaded to avoid being struck by spillage or falling materials. 1b. Ensure that operators are aware of their surroundings.Laborers working around equipment must be in positive contact with operator and wearing required PPE. 1c. All equipment will have audible back-up alarmes/devices. 2a. Excavated materials shall be placed at least 2-ft from edge of excavation. 2b. Protection (barracades) shall be provided to prevent personnel, vehicles and equipment from falling into excavations. 2c. Trenches will have means of egrees-ladders / benching / sloping. 2d. Trenches will be inspected daily by the competent person for conditions that could cause cave-ins or other unsafe conditions. 3a. During severe weather (rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Reinforcing Steel | P243 MISSILE MAGAZINES | 1. Crane use-Dropped loads, rigging failure, crane failure. 2.Tie back points to wall/column-Fall from hieghts | Reyes Construction Inc. SSHO- Ron Larson 909-837-8860 QCM- Jason Lee 909-837-7563 | 2022-05-09 | 2022-05-09 | II: Critical | D: Seldom | 3: MODERATE / MODERATE RISK (M) | 5/9/2022-04/30/2023 | Proper hand signals shall be used by qualified Signal Person Rigging shall be under the supervision of a Qualified Rigger / Pre-Hoist plan form will be completed by Qualified Rigger / Rigging shall be inspected before each use. Pre- Inspection of travel areas / Establish lay down area for reinforcing steel / Inspect all rigging prior to use. Tag lines shall be used to control all loads / Check crane and forklift certifications / Flagman and proper signage Secure all wall iron to strong backs or wall forms. Column guying will be done with wire cable or push pull rods, if necessary / Fall protection, full body harness, positioning device and double Y shock absorbing lanyard will be used above 6 ft. (100% tie off policy) | Continuing
FEAD LAAFB | Demolition | Relocate Main Gate | 1. Demo existing landscape, concrete and asphalt 2. Loading debris into trucks for haul off | JI Garcia Construction | 2022-06-06 | 2022-06-08 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 06/06/2022-10/20/2022 | 1a. Work will be supervised by a Competent Person &/or SSHO. 1b. Eye contact and proper hand signals must be kept at all times betweenm the equipment operator and signal persoon. 1c. All access ways will be kept free of materials, supplies and obstruction at all times. Tools, materials and debris shall be moved to avoid trip hazards. 2a. Eye contact and proper hand signals must be kept at all times between the equipment operator and signal person. 2b. Work shall be supervised by a competent person and/or SSHO. | Continuing
FEAD NWS Seal Beach(Fallbrook) | Excavations Trenching, Underground Utilities (Water) | Transite Waterline | 1. Caught inbetween equipment/crushed 2. Cave-ins | TeeHee SSHO-Josh Carroll 760-4531350 | 8/4/6/2022 | 2022-08-04 | I : Catostrphic | C: Occasional | 2: SERIOUS / HIGH RISK (H) | 8-2022 to 1-2023 | 1a. Workers shall stand away from vehicles being loaded or unloaded to avoid being struck by spillage or falling materials. 1b. Ensure that operators are aware of their surroundings.Laborers working around equipment must be in positive contact with operator and wearing required PPE. 1c. All equipment will have audible back-up alarmes/devices. 2a. Excavated materials shall be placed at least 2-ft from edge of excavation. 2b. Protection (barracades) shall be provided to prevent personnel, vehicles and equipment from falling into excavations. 2c. Trenches will have means of egrees-ladders / benching / sloping, as required. 2d. Trenches will be inspected daily by the competent person for conditions that could cause cave-ins or other unsafe conditions. 3a. During severe weather (rain storms, high winds, lightning) plans shall be made for evacuation of personnel and securing equipment. Winds 25mph+- or as deemed unsafe, Lightning 10-milesaway or less, Rain- deemed unsafe to slippery/wet, unsafe personnel exposure. | Continuing
FEAD NWS Seal Beach | Build Falsework/Scaffolding | P243 MISSILE MAGAZINES | 1. Set up - Scaffold failure 2. Working From Scaffolding - Fall Protection 3.Dismantling of scaffolding - Fall Protection | Reyes Construction Inc. SSHO- Ron Larson 909-837-8860 QCM- Steven Arteaga 909-762-2243 | 2022-08-22 | 2022-08-22 | II: Critical | D: Seldom | 3: MODERATE / MODERATE RISK (M) | 8/22/2022-2-22/2022 | 1. Inspect all scaffolding components for defects or damage; Remove damaged or defective components. 2. Keep guard rails and toe boards on all open side of scaffolding. Use body harness at exposed rail openings.Compotent person to inspect scaffold prior to use. 3. Fall protection when dismantling scaffold 6' and higher will be determined by compotent person. | Continuing
FEAD NWS Seal Beach | LHE for Post & Beam/Wedge Barrier System Crane Lift (Non Critical) | P-3018 LAAFB Relocate Main Entry Control Point | 1. Vehicle Traffic 2. Lifting/setting with forklift or mini-x 3. Crushing/caught between/equipment | J I Garcia Construction Scott Brueckner 559-474-2239 | 2022-08-02 | 2022-08-02 | II: Critical | D: Seldom | 3: MODERATE / MODERATE RISK (M) | 08/15/2022 - 11/15/2022 | 1a. Provide traffic control measures or shut down the access point. 1b. Ensure spotters/signalmen have relevant training & appropriate devices (signes, paddles, etc.) 2a. Conduct pre-lift meeting to review safety expectations. 2b. All personnel except riggers will stay outside of swing/lift zone. 2c. Always use at least one tag line to control the swing. | Continuing
FEAD NWS Seal Beach | Auger/Pre-cast light pole bases and new post/beam fence line posts | P-3018 LAAFB Relocate Main Entry Control Point | 2. Crushing/caught between/equipment | J I Garcia Construction Scott Brueckner 559-474-2239 | 2022-08-03 | 2022-08-03 | II: Critical | D: Seldom | 3: MODERATE / MODERATE RISK (M) | 08/15/2022 - 11/15/2022 | Employees to be trained on augering equipment, competent and certified person to operate skidsteer, spotter used when necessary; | Continuing
FEAD NWS Seal Beach | Scissor/Aerial Lift | B907 Paint & Bird Netting | 1: Fall from heights 2:Tipping hazards | Sapper West/Spectrum JV SSHO - Kevin Hankins (402) 230-2087 | 2022-09-20 | 2022-09-24 | II: Critical | D: Seldom | 3: MODERATE / MODERATE RISK (M) | 9/24/2022-12/15/2022 | 1: CP/QP/SSHO to inspect Lifts/Fall Protection Lanyards/Harness/etc. each day before use; 100% tie off required at all times; Workers prohibited from climbing on the rails 2: The area of operation shall be inspected for holes, penetrations and openings before operation begins | Continuing
NAF El Centro | Earth work, Adding AB to basin 348, Build slopes, ramp , etc | Basin repair | Struck by equipment, fall from heights, crushed by, heat stroke, heat exhaustion,heat cramps, sunburn | Spencer, Juan Herrera 520-576-7776 | 2022-08-16 | 2022-05-31 | II | C | 3 | Ongoing | Workers entering the job sote must wear a hard hat , safety glasses, class II reflective vest and safety toed work boots at all times,wear gloves at all time.Use of the 3 points of contact with the machine at all times, be speially careful in the rain or mud, whenever the machine is unattended the bucket/blades are lowered , brakes set, controls neutrailedand tthe engine is shut down.Make sure you always have an adequate supply of water available. | Continuing
NAF El Centro | Earth work, Adding AB to basin 344, Build slopes, ramp , heat raisen the temperature etc | Basin repair | Heat stroke , heat exhaustion , heat cramps , hazards and mitigating not communicated to the employees , employees not aware of scope of work and / or porcess | Spencer, Juan Herrera 520-576-7776 | 2022-08-17 | 2022-05-31 | II | C | 3 | Ongoing | Make sure you always have an adequate supply of water available .If your water supply is running low talk to your supervisor , drink plenty of water or fluid throughout the day. Use of suncreen. Knowwhere the emergency numbers are posted , where the first adi kit is and who is trained in first aid.TBT mandatory attendance must be conducted before work commences, all employees must review and sign all documents . Any questions or concerns must be brought to the attention of the supervisor immediately | Continuing
NAF El Centro | Earth work, Adding AB to basin 346, Build slopes, ramp ,temperature is risen etc | Basin repair | Striking and injuring co-workers with equipment or material,slip, trips falls , miscommunication with the operator,eat , heat exhaustion, heat cramps | Spencer, Juan Herrera 520-576-7776 | 2022-08-19 | 2022-05-31 | II | C | 3 | Ongoing | be aware of the location of workers in and around the excavation at all times.Stand away from the equipment that is loading or unloading excavated material ensure to have proper footing next to trench and on slopes or hills.ensure to have footing next to trench bevore cutting roots,always have a good communication with operator, mark areas of the trench that could have possible cave-ins watch swing radius of equipment that is working in our area.make sure you always have an adequate supply of water available , if your water supply is running low talk to your supervisor , drink plenty of water or fluids throughout the day, use sunscreen. | Continuing
NAF El Centro | Earth work, manage AB to the basins , and set up the forms on 348 for the pour | Basin repair | Struck by equipment, fall from heights, crushed by, heat stroke, heat exhaustion,heat cramps, sunburn | Spencer, Juan Herrera 520-576-7776 | 2022-08-30 | 2022-05-31 | II | C | 3 | Ongoing | Workers entering the job sote must wear a hard hat , safety glasses, class II reflective vest and safety toed work boots at all times,wear gloves at all time.Use of the 3 points of contact with the machine at all times, be speially careful in the rain or mud, whenever the machine is unattended the bucket/blades are lowered , brakes set, controls neutrailedand tthe engine is shut down.Make sure you always have an adequate supply of water available. | Continuing
ROICC TRAVIS/SF | UXO stockpile clearing,Work in RCA | N62473-17-D-0005-N62473-18-F5271, Treasure Island, SWDA Westside, IR Site 12 | UXO hazardaous fragment distance, Construction Equipment | Gilbane, Asish Mogera 925-946-3172 | 2021-03-15 | 2021-03-15 | EH | M | EH | Start: 03/15//2021 Finish: 10/22/2023 | Workers underwent site orientation, conducted Site Specific Rad training and UXO crew received rad + MPPEH training. UXO crew will utilize conx boxes for use as barriers during UXO screening tasks. Proper PPE at all times, Rad tech to scan and clear all equip/personel prior to exiting RCA. | Ongoing
ROICC TRAVIS/SF | Steel Building Erection | N62473-1-D-5855, Regional Maintenance Training Facility | Crushed by, struck by, pinch point, failling | SOLTEK PACIFIC Joe Thieme 619-971-5738 | 2022-06-22 | 2022-06-22 | M | L | M | Start: 6/22/2022 Finish: 09/29/2023 | Installers are trained and certified to perform the work safely and competently. All site personnel wearing high vis vests/class II reflectors and operators must be aware of surroundings. Inspect rigging and equipment daily and ensure proper communication between team. Inspect and properly utilize all fall protection equipment and PPE. | Continuing
ROICC TRAVIS/SF | Trench Excavation/Crawl space of building radiological scanning | N62473-17-D-0006 CTO N6247318F5065 Parcel G, Rad Investigation, Survey in Hunters Point, SF CA | COVID, Struck-By, Caught Between, Fall Hazards, Cave-Ins, Chemical Exposure Concerns, Underground Utility line, Dust | Aptim/CB&I FEDERAL SERVICES: Paul DeOcampo (Cell) 916- 837-7195. | 5/312022 | 2022-06-01 | M | M | M | Start: 05/24/2020 Finish: 12/31/2022 | Trenchs excavation for Radiological investigation in Parcel G is ongoing, the contractor is following the approved APP/AHAs and COVID 19 protection plan. CM/QA CM site visits on a regular basis. | Ongoing
ROICC TRAVIS/SF | Install Vertical Lift Fabric Door (VLFD) | N62473-20-C-0613 -- KC-46 3-Bay Maintenance Hangar | Stuck By, Pinch Points, Caught Between, Noise, Falls, Heavy lifting | Walsh Federal, LLC: Emmanuel Soco | 2022-09-12 | 2022-09-12 | M | M | M | Start: 06/12/21 Finish: 10/21/22 | Subcontractor will have all employees review the AHA before beginning work. Subcontractor is performing safety briefs to ensure appropriate PPE is being used for the activities such as eye wear, gloves, hearing protection and attire as needed for the task. Inspect all equipment for DFoW. Motors being lifted in place with crane, Dailiy inspection of crane conducted, Manlifts inspected dailiy and using fallprotection as perscribed. | Ongoing
FEAD Lemoore | Excavation/Trenching | N62473-21-C-1011 Hangar 6B Extension | Engulfment | Harper Construction Michael Castillo | 2022-01-24 | 2022-01-24 | E | M | H | 24JAN2022-30MAR2024 | Competent person shall perform a daily Inspection of the excavation, the adjacent areas, and all protective systems before each shift and after each hazard increasing occurrence such as rain. | Continuing
FEAD Lemoore | Excavation/Trenching | Inlet Works N2647319D1201 TO#N6247322F4129 | Engulfment | Ed Odoya | 2022-03-01 | 2022-03-01 | E | M | H | 01MAR2022-01DEC2022 | Competent person shall perform a daily Inspection of the excavation, the adjacent areas, and all protective systems before each shift and after each hazard increasing occurrence such as rain. | Continuing
FEAD Lemoore | Pull Medium Voltage Cable in manhole | P-3271 Electrical Upgrade N62473-17-D-4617 TO N62473-20F-4079 | Electric shock from existing energized Medium Voltage Cable, flammable gasses, lack of oxygen. | T&D / Synergy SSHO Mike Pendegras | 2022-01-18 | 2022-07-05 | E | M | H | 05JUL2022-31AUG2022 | Attendant (Jorge Guzman/Ben Swanson, Mike Pendergrass, Jake Morse, Andy McComas) will Don 8 cal clothing, and verify that the atmospheric conditions are still stable in manhole/vault. Qualified Electrician (Jake Morse, Andy McComas) wearing a 40 cal arc flash suit, 12kv insulating gloves, leather gloves, and safety toe boots is to don Arc Rated Fall Protection Harness and properly be connected to Rescue Tri-Pod. | Continuing
FEAD Lemoore | Welding/Cutting | N62473-21-C-1011 Hangar 6B Extension | Fire, explosion, burns | Harper Construction Michael Castillo | 2022-05-09 | 2022-05-09 | E | M | H | 09MAY2022-30MAY2023 | Obtain Hot work Permit from installation fire authority prior to the start of welding, cutting, or grinding operations. Assign trained fire watch personnel on use of firefighting equipment and in sounding an alarm in the event of a fire. Provide suitable fie extinguisher of sufficient capacity. | Continuing
FEAD Lemoore | Non-destructive testing of Fuel Pipeline using Gamma Radiography | N62473-21-C-1011 Hangar 6B Extension | Radiation exposure to workers | Harper Construction Michael Castillo | 2022-05-09 | 2022-05-09 | E | M | H | 09MAY2022-30 NOV2022 | Utilize identified boundary cones, ropes, or barrier tape depending on the site layout. Per Federal and Agreement State regulations, during radiographic exposures there must be 2 qualified individuals in or around the controlled areas to ensure no public entry into any area where they could receive a dose equivalent to more than 2mR in any one hour. In the event a controlled radiation area is breached by a member of the public the Radiographer is to immediately retract the sealed source into the stored position, Stop Work and contact the RSO to conduct a member of the public exposure investigation. | Continuing
FEAD Lemoore | Steel Erecting | N62473-21-C-1011 Hangar 6B Extension | Crane Lift and Steel Erection | Harper Construction Michael Castillo | 2022-07-08 | 2022-07-08 | M | L | M | 12July2022 - 28Mar2023 | O'Brien to lift and place Structural Steel for the Hangar and have begun in Quadrant 1 and will continue to move North into Quadrant 2. Once Quadrants 1 & 2 are completed W&W steel will begin to work on the Hangar Bay (Quadrant 3 and continue North into Quadrant 4) There is currently a hot work permit for this project, listed directly above. | Continuing
FEAD Lemoore | Scaffolding | N62473-21-C-1011 Hangar 6B Extension | Falls From Elevated Heights | Harper Construction Michael Castillo | 2022-07-20 | 2022-07-20 | E | M | H | 20July2022-20Nov2022 | Competent person shall perform a daily Inspection of the Scaffolding, the adjacent areas, and all protective systems before each shift and after each hazard. | Continuing
FEAD MIRAMAR | Confined Space Operations | P-250 Child Development Center MCAS Miramar, CA | Low oxygen, Oxygen rich, Toxic environment | RQ Construction Troy Brandt SSHO | 2022-04-20 | 2022-04-20 | C | S | M | Start 09-08-22 Complete 10-30-22 | ET Oversight, coordinate with base safety | Continuing
FEAD MIRAMAR | Building Energization | P-250 Child Development Center MCAS Miramar, CA | Burns, Shock or Electrocution | RQ Construction Troy Brandt SSHO | 09/05/22 | 2022-09-05 | C | S | M | Start 09/06/22 Complete 10/19/22 | LOTO rules enforced by ET | Continuing
FEAD MIRAMAR | Fall Hazard | Replace Fire Alarm System B-8402 | Fall From Heights/Man Lift | South West Dakota. | 2022-10-04 | 2022-10-04 | C | U | L | Start: 10/02/22 Complete 10/27/22 | ET Oversight | NEW
FEAD MIRAMAR | Confined Space Operations | AT&T Fiber Pull | Low oxygen, Oxygen rich, Toxic environment | Bachtel/AT&T | 2022-10-12 | 2022-10-12 | C | S | M | Start: 10/12/22 Complete: 10/31/22 | ET Oversight | NEW
FEAD MIRAMAR | Fall Hazard | Housing Lighting Project | Fall From Heights/Man Lift | West Development | 2022-10-12 | 2022-10-12 | C | U | L | Start: 10/12/22 Complete: 10/17/22 | ET Oversight | NEW
FEAD MIRAMAR | Confined Space Operations | B9176 Pipe leak | Low oxygen, Oxygen rich, Toxic environment | Twins | 2022-10-13 | 2022-10-13 | C | S | M | Start: 10/18/2022 Complete: 10/20/2022 | ET Oversight and coordination with base safety | NEW
FEAD 29 Palms | HIGH: lift HVAC units to roof with a crane | N6247319D1222-N6247321F4772 Repair Vehicle Maint Fac B1206 (TP17001M) | Falling from heights, injuries from heavy equipment | Gideon Contracting LLC. Chris William (928)315-2611 | Completed 10/17/2022 | Completed 10/17/2022 | C | S | M | 10/25-10/28/2022 | Crane lift at B1206 on 10/25/22 - FEAD will conduct daily Safety Oversight. Contractor will follow the accepted AHA. Contractor to perform Daily inspections of PPE (fall protection gear) during installation of HVAC units on roof. Rigging equipment, including tag lines shall be inspecteddaily during crane operation by a Competent Person before each use and as necessary during its use. High visibility vests will be worn by personnel during crane operations. Any defective equipment shall be removed immediately from service. This is not a critical lift. | New
FEAD Yuma | Control of Hazardous Energy (Lockout/Tagout) | P-596 Hanger 95 Project N6247317D0871 | Temp Building Power | Harper Construction SSHO: Ryan Armer 619-430-0166 | 2021-02-09 | 2021-03-22 | M | U | L | 06/07/2021 - 12/15/2022 | Hot work Permits issued, fire extinguisher within 25' of operations, fire watch posted 30 min after operation | Continuing
FEAD Yuma | Hot Work | P-596 Hanger 95 Project N6247317D0871 | Plumbing, Electrical, Structural Steel, Masonry Footings, Framing | Harper Construction SSHO: Ryan Armer 619-430-0166 | 2021-07-21 | 2022-09-30 | M | U | L | 06/21/2021 - 12/30/2022 | Hot work Permits issued, fire extinguisher within 25' of operations, fire watch posted 30 min after operation | Continuing
FEAD Yuma | Trenching/Excavation | P-596 Hanger 95 Project N6247317D0871 | Earthwork & Underground Utility, Concrete Pads & Footings | Harper Construction SSHO: Ryan Armer 619-430-0166 | 2021-06-04 | 2021-09-07 | N | S | L | 04/09/2021 - 11/30/2022 | Trenching plan will be established for tenching over 5 feet with proper means of protection approved and onsite prior to start of work. Means of egress will be in place then trench reaches 4 feet or deeper. MCAS Yuma Soil classifacation in class C. No Benching allowed | Continuing
FEAD Yuma | Fall Protection | P-596 Hanger 95 Project N6247317D0871 | Electrical, Plumbing, Structural Steel, Decking, Roofing, HVAC, Framing | Harper Construction SSHO: Ryan Armer 619-430-0166 | 2021-03-24 | 2021-07-14 | M | U | L | 06/15/2021 - 12/30/2022 | 3g. Follow manufacturer’s instructions and the requirements from the EM 385-1-1 when working from ladders. Fall Protection PPE is to be worn when using powered scaffolds or aerials as instructed by the manufacturer and the requirements of the EM 385-1-1. Personnel operating equipment shall have the appropriate training for the equipment being used. EM 385-1-1, 21.J | Continuing
FEAD Yuma | Aerial Lifts (Crane Lifts) | P-596 Hanger 95 Project N6247317D0871 | HVAC, Plumbers, Electricians, Framers | Harper Construction SSHO: Ryan Armer 619-430-0166 | 2021-12-14 | 2021-12-17 | M | U | L | 06/21/2021 - 12/30/2022 | A restraint system shall be used in addition to guardrails. The lanyards, to include lanyards with built-in shock absorbers, used with the restraint system shall be sufficiently short to prohibit workers from climbing out of, or being ejected from the platform. | Continuing
FEAD Yuma | Control of Hazardous Energy (Lockout/Tagout) | P-612 Hanger Project N6247319F4705 | Electrical | Harper Construction SSHO: Bruce Winder (619) 241-1528 | 2022-08-01 | 2022-08-01 | M | U | L | 06/07/2021 - 12/30/2022 | All Energized equipment to be de engergized by I & LOTO will consist of coordination bewtween I & L and eletrical contractor. All de-energized sources to be tested and bled of any residual energy | Continuing
FEAD Yuma | Hot Work | P-612 Hanger Project N6247319F4705 | Plumbing, Roof/Wall Panels, Framing, Misc Steel, Site Concrete | Harper Construction SSHO: Bruce Winder (619) 241-1528 | 2022-08-29 | 2022-09-06 | M | U | L | 01/01/2020 - 12/30/2022 | Hot work Permits issued, fire extinguisher within 25' of operations, fire watch posted 30 min after operation | Continuing
FEAD Yuma | Fall Protection | P-612 Hanger Project N6247319F4705 | Electrical, Plumbing, HVAC, Fire S., Roof/Wall Panels, Framing, Misc Steel | Harper Construction SSHO: Bruce Winder (619) 241-1528 | 2022-09-01 | 2022-09-06 | M | U | L | 10/01/2020 - 12/30/2022 | 3g. Follow manufacturer’s instructions and the requirements from the EM 385-1-1 when working from ladders. Fall Protection PPE is to be worn when using powered scaffolds or aerials as instructed by the manufacturer and the requirements of the EM 385-1-1. Personnel operating equipment shall have the appropriate training for the equipment being used. EM 385-1-1, 21.J | Continuing
FEAD Yuma | Crane/Rigging Safety | P-612 Hanger Project N6247319F4705 | Roof/Wall Panels, Storm Chamber, Misc Steel | Harper Construction SSHO: Bruce Winder (619) 241-1528 | 2022-09-01 | 2022-09-06 | M | U | L | 01/21/2021 - 12/30/2022 | Rigging Chains/nylon slings - Inspections shall be made as per Manufacturers recommendations and EM 3851-1 section 15.E & 15 G. C. Only qualified riggers will rig loads. Operators - Mobile crane operator are certified. In addition the operator will posses a current commercial drivers license (CDL) and medical card. | Continuing
FEAD Yuma | Aerial Lifts (Crane Lifts) | P-612 Hanger Project N6247319F4705 | Electrical, Roof/Wall Panels, HVAC, Fire S., Misc Steel | Harper Construction SSHO: Bruce Winder (619) 241-1528 | 2022-08-29 | 2022-09-06 | M | U | L | 06/28/2021 - 12/30/2022 | 22.M.02 Shall be operated, inspected, tested, and maintained as specified in the operating manual. Records of inspections conducted while the unit is at the work site shall be maintained at the work site. All required safety decals, labels and signs shall be in place and readable | Continuing
NAF El Centro | Working From Hieghts | Repainting inside of Sports Center, BL.332 | Falls from upper levels, Struck by | KJS support Services Joaquin Rangel (760)604-5685 | Completed 07/07/2022 | Completed 07/15/2022 | II | C | 3 | 07/18/22-07/30/22 | Fall Protection will be used when working on Scissor Lift. Gym area will remain closed to patrons until painting and repairs are completed | Complete
NAF El Centro | Excavation | Repair water leak next to building 188 Pump House. | Electrocution, Hitting utility lines, Cave-ins,Hazardous Atmospheres, Engulfment | KJS support Services Joaquin Rangel (760)604-5685 | Completed 08/01/2022 | Completed 02/17/2022 | II | C | 3 | 08/08/22-09/03/22 | Contractor will follow requirements as per OSHA and USACE relating to excavation practices, personnel will comply with rules outlined in the Hazardous Energy Control Program,Lockout/tagout proceedures will be used to isolate water source during repairs, Area will be monitored with gas meter as required,Sump pumps will be used to remove water from inside excavation . | Complete
NAF El Centro | Confined Space | Access electrical vault located between hanger 2 and hanger 3 | Electrocution, Burns,Asphyxiation, | KJS support Services Joaquin Rangel (760)604-5685 | Completed 09/22/2022 | Completed 02/10/2022 | II | C | 3 | 09/22/22-09/27/22 | The space will be aired out with blower,space will be monitered with gas sensor and worker will use harness tied to Tripod,Lockout Tagout will be performed as required,Electrical testers will be used to verify | Complete
FEAD Camp Pendleton | Fall Protection | N6247317D0817/18F5298 | Inproper use fall protectin | Harper Construction | 2021-10-20 | 2022-10-29 | M | S | L | 10/20 - 12/29/2022 | Fall protection plan & AHA reviewed by all employees | Continuing
FEAD Camp Pendleton | Grading | N6247317D0817/18F5298 | Run over by Equipment, Stuck by, Cave in. | Harper Construction | 2021-10-20 | 2022-12-29 | M | S | L | 10/20 - 12/29/2022 | AHA has been reviewed. SSHO will be on site during activities Spotter are in use when backing up | Continuing
FEAD Camp Pendleton | Aerial work platform | N62473-20-C-0055 | Not tied in, uneven surface | RQ Construction | 2021-10-20 | 2021-10-20 | M | S | L | 10/20/21-10/20/2022 | SSFPP AHA Training for lift all reviewed by crew | Continuing
PWD NBSD FEAD | Excavation and Trenching for Electrical Cabling / Ductbank. Cutting steel / metal and Roof Work | P-0888, Harbor Drive Switching Station Replacement | Injury and property damage from trench collapse, striking existing underground gas line. Electrocution | Helix Electric Inc. | 2020-03-11 | Initial Training Completed 09/9/2019 | Cat | S | H | 9/9/2019 - 11/31/2022 | Excavation / Trenching Plan, Subsurface, mark out, excavation request, and Fall Protection Plan will be submitted to Government for review and acceptance prior to beginning operations. Near Energized Permit was accepted by NAVFAC CO. Safety Plan and AHA's accepted by Government for near energized work. Competent Person shall inspect the electrical site and adjacent areas, and protective systems daily and have approved traffic control in place. Competent Person shall inspect the excavation, the adjacent areas, and protective systems daily. Hot work permit obtained by contractor prior to starting hot work activities. Workers will review AHA's (Activity Hazard Analysis); will be wearing proper PPE, and will be briefed daily to adhere to the activities for the day. | Continuing
PWD NBSD FEAD | Scope includes demolition and replacement of Pier 6. Pile driving , Critical Crane Lifts, trenching for electrical, Near-energized work, demolition of cables and mandrel of conduits. | Pier 6 Replacement | Injury and property damage from falling material being lifted, collapsed of trench, and electrocution. | Manson Construction | 2021-09-20 | Initial Training Completed 09/13/2021 | CAT | U | H | 9/27/2021 - 9/17/2023 | Crane lift plan approved by NAVFAC Crane inspectors. NAVFAC Crane inspectors will inspect Crane and Rigging prior to Crane Operations. Crane swing will stay away from Electrical cables and other overhead obstruction and maintain proper swing clearances. Near Energized Permit / request was approved by NAVFAC CO. Safety Plan and AHA's submitted to Government was accepted for near energized work. Competent Person shall inspect the electrical site and adjacent areas, and protective systems daily. Demolition Plan, Safety Plan and AHA's submitted to Government for review and acceptance prior to beginning demolition operations. Utility Safe-Offs and Lock Out / Tag Out performed prior to demolition. Competent Person shall inspect the demolition and adjacent areas, and protective systems daily. Hot work permit obtained by contractor prior to starting hot work activities. Excavation / Trenching Plan, Subsurface, mark out, excavation request, and Fall Protection Plan will be submitted to Government for review and acceptance prior to beginning operations. Have approved traffic control in place. Competent Person shall inspect the excavation, the adjacent areas, and protective systems daily. Workers will be wearing proper PPE including personal floatation devices and will be briefed daily to adhere to the activities for the day. | Continuing
PWD NMCSD, NBSD FEAD | Elevated and Hot work | Seismic Rehab, Bldgs 2 South & 3 North, NMCSD | Injury and property damage from debris and falling material; Fire damage. | Soltek Pacific Construction Co. | 2022-06-02 | Training Completed 6/6/2022 | Cat | S | H | 06/06/2022 - 04/05/2024 | AHA's and Fall Protection Plan submitted to Government for review and acceptance prior to beginning of activities. Obtain hot work permit as required. Workers will review AHA's (Activity Hazard Analysis); will be wearing proper PPE, and will be briefed daily to adhere to the activities for the day. | Continuing
PWD NBSD FEAD | Electrical Outage to install recording meters | B-76 Redistribute Power to HVAC and Electrical Panels | Injury and property damage from electrocution / fire. | Heffler Contracting Group. | 2022-10-03 | Initial Training Completed 10/05/2022 | Cat | U | H | 2022-10-22 | Electrical Outage plan / request must be reviewed and approved by NAVFAC. Safety Plan and AHA's submitted to Government for review and acceptance prior to electrical outage operations. Utility Safe-Offs and Lock Out / Tag Out performed prior to start of activity. Competent Person shall inspect the electrical site and adjacent areas, and protective systems daily. Workers will be wearing proper PPE and will be briefed daily to adhere to the activities for the day. | New
FEAD China Lake | Placing Concrete | N62473-19-D-2438/N6247320F4817 (CONSTR) P810-RUNWAY & TAXIWAY EXTENSION - NAWS China Lake, CA | Heavy Equipment | Baldi Bros (Kevin)(Yoo) | 2020-09-29 | 2020-09-29 | M | U | L | 12/28/2021-03/01/2023 | Contractor competent person on site. Daily ET job site checks | Continuing
FEAD China Lake | Working at Heights/Hot Work | CONSTR; Boiler Plant 4 Major Repairs, NAWS China Lake Earthquake Recovery | Fall Hazard/Hot Work | I E Pacific Inc. (Rich)(Miguel) | 2021-02-23 | 2021-02-23 | M | U | L | 02/23/2021-10/21/2022 | Demo plan approved. Contrator competent person on site. Daily ET job site checks. | Continuing
FEAD China Lake | Roofing, Interior Framing | N62473-19-D-1222/N6247321F5359 D7J00520MR REHAB MJH30 (EAST) BLDG. BLOCK 4 | Fall Hazzard | Gideon Contracting LLC (Kevin)(Julie) | 2022-05-02 | 2022-05-02 | CAT | U | L | 06/07/2022-12/25/2022 | Fall Protection Plan approved. Contractor competent person on site. Daily ET job site checks | Continuing
FEAD China Lake | Roofing, Interior Framing | N62473-19-D-1222/N6247321F5360 CONVERT MJH10 EAST BLOCK #2 TO OFFICE SPACE, FAC. 02885 | Fall Hazzard | Gideon Contracting LLC (Kevin)(Julie) | 2022-05-02 | 2022-05-02 | CAT | U | L | 06/07/2022-12/25/2022 | Fall Protection Plan approved. Contractor competent person on site. Daily ET job site checks | Continuing
FEAD China Lake | Trenching | N62473-18-D-5818/N6247320F5332 Construct WTO Secure Facility (LB1b) | Heavy Equipment | Pacific West Builders (Simons)(Miguel) | 2022-10-17 | 2022-10-17 | CAT | U | L | 10/17/2022-12/17/2022 | Contractor competent person on site. Daily ET job site checks | New
FEAD China Lake | Trenching | N62473-18-D-5823/N6247321F4232 D491D029 - Construct Lunchbox (LB1a) Secure Facility to Support F-18 IPT | Heavy Equipment | I E Pacific Inc. (Simons)(Miguel) | 2022-10-17 | 2022-10-17 | CAT | U | L | 10/11/2022-10/19/2023 | Contractor competent person on site. Daily ET job site checks | New
PWD Point Loma | Hot Work | N62473-18-D-5829 TO N6247321F5477 Replacement FSII System to Higher Flow Rates Naval Base Point Loma San Diego, California | Risk of fire and burns from open flames, sparks or heat. | Pond: Vicente Alvarez (770) 864-6830 Govt: Christian Konn (619) 813-0527 | 2022-10-18 | 2022-05-15 | M | L | M | 10/17/2022-5/09/2023 | Safety Plans/AHAs associated have been reviewed and accepted. Preparatory and safety meetings held. Safety training provided regarding trenching and excavating. Safety training provided regarding hot work. Hot permits are issued the day of by Fed Fire. A designated fire watch will monitor site 1 hour after hot work has been finished for the day. | New
PWD Point Loma | Brush Removal Working near overhead electrical lines | Wild Fire Clearance around electrical substation | Tree climbing Fall from heights Dropped load Snake bite Electric Shock | LTS Grounds Jose Ramirez (562)746-9484 NAVFAC SPAR Mark Nefalar (619)524-3467 | 2022-10-18 | 10/11/2022 - 11/7/2022 | M | L | M | 10/11/22 -11/7/2022 | Safety Plans/AHAs associated have been reviewed and accepted. Preparatory and safety meetings held. All tree work operations above a height of 12 ft (3.6 m), whether there are electrical hazards or not, shall require a second worker in the area. If climbing is being performed, the second worker shall also be a qualified climber, capable and knowledgeable of rescue techniques, including self rescue. (EM385-1-1 31.B.01.A). All workers will ensure proper restraints are added onto the trees to prevent dropped loads. A hazard area has been designated in the event one does occur. A ground guide will give verbal and hand signals to allow proper communication. 1ST responders will be contacted and a BLS certified individual will be on site.(EM 385 1-1 21A-F). Safe electrical approach distances will be maintained at all times. | Continuing
PWD Point Loma | In water work crane and barge operations | N62473-16-D-1806 TO N6247320F4932 Structural Pier Repairs | Daily travel on boat, vessel traffic, man overboard, drowning, hypothermia, low visibility, physical injury, Dysbarism | R.E. State Engineering: Jeff Casey (415) 559-5452; Govt: Martin Lemon (619) 571-2408 | 2022-10-18 | 2022-04-26 | M | L | M | 6/28/2021-11/25/2022 | Safety Plans/AHAs associated have been reviewed and accepted. Preparatory and safety meetings held. Safety training provided regarding crane and water work specific hazards. | Continuing
PWD Point Loma | Confined Space Entry | N39430-20-D-2225 TO N3943020F4031 Point Loma Seed Task Clean, Inspect, and Repair Fuel Tanks | Toxic Atmosphere. A toxic atmosphere may cause various acute effects, including impairment of judgement, unconsciousness and death. Oxygen Deficiency, Oxygen Enrichment, Flammable or Explosive Atmospheres, Flowing Liquid or Free Flowing Solids, Excessive Heat. | APTIM Federal Services Carlos E. Bernal (520) 366-2902 Govt: Christian Konn (619) 813-0527 | 2022-10-18 | 2022-08-29 | M | L | M | 8/29/2022-12/02/2022 | Safety Plans/AHAs associated have been reviewed and accepted. Gas Free Engineer certification issued on site. | Continuing
PWD Point Loma | Excavation and Trenching Multi-purpose Machine Rigging | N62473-19-D-1203 TO N6247321F4717 Repair Underground Force Main Sewer Line, NBPL | Cave-ins, Falling into the trench or excavation, Flooding or water accumulation, Contact with buried service lines such as electrical, natural gas, water, sewage, telecommunications, etc. Moving parts and equipment, Loads not safely rigged before being hoisted, Improper use of tag line allowing hoisting material to swing out of control, Loads swung or suspended overhead, Hazardous locations between a swinging load and fixed object. | Transtar Pipeline and Orion Construction: Josh Cooper (760) 505-0397 Govt: Christian Konn (619) 813-0527 | 2022-10-18 | 2022-05-16 | M | L | M | 5/16/2022-11/16/2022 | Safety Plans/AHAs associated have been reviewed and accepted. Preparatory and safety meetings held. Safety training provided regarding trenching and excavating. Safety training provided regarding rigging with multipurpose machines. Associated forms have been submitted to the crane safety shop. | Continuing
PWD Point Loma | Working at heights | N62473-20-D-0041 Roofing Projects NBPL-377 | Falling from heights, Moving and operating heavy machinery, Falling objects, Dust Inhalation, Eye Injury, Cuts/Scrapes, Struck By, Caught Between object, Shock from tools | ARWI: Jessica Willkom (619) 957-1014 Govt: BU2 Monica Lupkin (228) 213-0853; Arnold Henson (858) 924-2291 | 2022-10-18 | 2022-06-28 | M | L | M | 06/28/2022-12/28/2022 | APP, FPP, AHA plan have been approved and accepted. Preparatory and safety meetings will be held. 100% tie off will be followed. Training regarding fall protection and working from heights will be provided first day on the site. | Continuing
PWD Point Loma | Working at heights | N62473-22-D-3421 TO N6247322F9503 BRIG-7684 Repair/Replace Concertina Wire | Falling, tools falling, spinal &head neck injuries, platform collapse, Falling debris, Fatigue, tip over | BULL FENCE : Josh Flud (760) 801-4589 Govt: Martin Lemon (619) 571-2409 | 2022-10-18 | 2022-09-20 | M | L | M | 9/20/2022-12/31/2023 | APP, SSFPP, /AHAs associated have been reviewed and accepted. Preparatory and safety meetings held. Safety training provided regarding working from heights, 100% tie off will be followed. | Continuing
PWD Point Loma | Working at heights | N62473-18-D-5819 TO N6247319F5044 NBPL-619 Construct ISR Lab | Falling, tools falling, spinal &head neck injuries, platform collapse, Falling debris, Fatigue | Dimensions Construction Inc: Tom Walker (619) 840-0609 Trailer (619) 553-5772 Govt: Martin Lemon (619) 571-2409 | 2022-10-18 | 2022-04-26 | M | L | M | 1/06/2022-11/08/2022 | Safety Plans/AHAs associated have been reviewed and accepted. Preparatory and safety meetings held. Safety training provided regarding scaffolding and working from heights | Continuing
PH-2 | HIGH/HEAVY/OUTAGE: lift chillers to roof with a crane, work with power tools and building power outage | N62473-10-D-2605 TO# 12F4088 PH 2 | Falling from heights, injuries from heavy equipment, power tools, building electrical | MIK | 2022-10-05 |  | I | C | II | ESD: 10/17/2022 ECD: 12/30/2022 | Crane lift at PH2 on 10/03/22 - FEAD will conduct daily Safety Oversight. Contractor will follow the 5 steps of ORM and adhere to the GDA accepted AHA. KTR to perform Daily inspections of PPE (fall protection gear) during installation of chiller on roof. Rigging equipment, including tag lines shall be inspecteddaily during crane operation by a Competent Person before each use and as necessary during its use. High visibility vests will be worn by personnel during crane operations. Any defective equipment shall be removed immediately from service. All Tools and Equipment on a daily basis during operations. Contractor will check for LOTO when removing existing equipment and installing HVAC units. F.Acosta 10/17/2022 | CONTINUING
PM Hangar 34 | HIGH: install AFFF piping in hangar | N62473-16-D-1874 18F4048 | Falling from Heights | SW Dakotah, Tony Acosta | 2022-02-24 | 2022-02-24 | N | S | L | ESD: 02/24/2022 ECD: 01/05/2023 | Airfield Safety Waiver approved for laydown and temporary construction area on west side of North Hangar as of 05/31/2022. FEAD will conduct daily Safety Oversight. Contractor will follow the 5 steps of ORM and adhere to the GDA accepted AHA. KTR to perform Daily inspections of PPE (fall protection gear), Tools and Equipment. Contractor will check equipment each day. Tolle 10/18//22 | CONTINUING
PM-373 | - HIGH: roof installation - DEEP Trenching | N62473-17-D-4628 21F4447, PM373 | Falling from Heights / Trenching and Utility work | I.E Pacific | 2022-08-15 | 2022-10-30 | I | C | 2 | ESD: 08/29/2022 ECD: 11/30/2022 | Work in any trench or excavation MUST be under the direct supervision of a Competent Person with experience in this type of work. Follow proper trench and excavation procedures. Inspect trench or excavation prior to entry to ensure it is safe. Access must be provided for any trench or excavation deeper than 4 feet. Ladder must be placed at each end and must not be further than 25 feet apart. Ladders shall extend 36” above opening/surrounding ground and be secured. Trench and excavations deeper than 5 feet must be either, sloped, shored or shielded. Spoils must be kept back a minimum of 2 feet. Warning Signs and appropriate barricades must be posted around all open excavations and trenches.Workers exposed to fall hazards shall be protected from falling to a lower level, and, whenever workers are exposed to falls from unprotected sides or edges unprotected roof edges. In all roof work, fall protection systems shall be provided to prevent falling from the roof.. Before work begins, a CP for Fall Protection will make a dailyinspection of the job site). Personal Protective Systems and Equipment to be inspected daily and logged and defective or damaged fall protection gear and equipment to be taken out of service. fall protection gear properly stored according to manufacturer recommendations Work on the roof shall be halted during severe weather, high winds, and rain. The Contractor will conform to the standards of EM385 Section 23 and adhere to GDA approved Fall Protection Plan and AHAs. KTR to perform Daily inspections of PPE, Tools and Equipment. FEAD will conduct daily Safety Oversight. F.Acosta 10/17/2022 | CONTINUING
PH-1517 | OUTAGE: change out switchgear | N62473-17-D-4630 21F4564, PH-1517 | Electrocution | Bilbro Construction Company | 2022-10-12 | 2022-10-12 | M | S | M | ESD: 10/20/2022 ECD: 10/20/2022 | Replace swirchgear at PH-1517. This will affect the whole BEQ Complex of PH-1517, 1518, 1519, and 1520. FEAD will conduct daily Safety Oversight. Contractor will follow the GDA accepted AHA. All circuits or equipment must be locked out and tagged out before beginning work on those circuits or equipment. Tag should have your name, the date and time on it. Check that there are no hot wires or equipment at the location of the work using a meter to check for any energy still coming in. Refer to Site HECP (Lock out Tag out) plan for details. Rosnov 10/19/2022. | CONTINUING
PM-160 | DEEP: Trenching for underground electric and water | N62473-19-D-1220 21F4205 | Hitting underground utilities | Ahtna | 2022-10-05 | 2022-10-05 | M | S | M | ESD: 09/27/2022 ECD: 11/10/2022 | Excavation and Trenching Competent Person will oversee this work. Follow proper trench and excavation procedures. Inspect trench or excavation prior to entry to ensure it is safe. Work is not expected to go deeper than 5 feet, but shoring or shielding will be used if it is needed. Spoils must be kept back a minimum of 2 feet. Warning Signs and appropriate barricades must be posted around all open excavations and trenches.Workers exposed to fall hazards shall be protected from falling to a lower level, and, whenever workers are exposed to falls from unprotected sides or edges unprotected roof edges. Contractor shall perform Daily inspections of PPE, Tools and Equipment. FEAD will conduct daily Safety Oversight. On hold due to a Suspension of work order from the Contracting Officer as of 10/06/2022. (The site currently has open trenches with a perimeter fence.) Chung 10/18/2022 | HOLD
PM-333 | OUTAGE: Remove power monitroing equipment at main breaker, panel RP-F, and Panel M2. | N62473-19-D-2444 22F4849 | Electrocution | Cody Stevens Construction, Inc., Rolando Quizon | 2022-10-18 | 2022-10-18 | M | S | M | ESD: 10/31/2022 ECD: 10/31/2022 | FEAD will conduct daily Safety Oversight. Contractor will follow the GDA accepted AHA. All circuits or equipment must be locked out and tagged out before beginning work on those circuits or equipment. Tag should have your name, the date and time on it. Check that there are no hot wires or equipment at the location of the work using a meter to check for any energy still coming in. Refer to Site HECP (Lock out Tag out) plan for details. Kim 10/19/2022. | NEW
PH-1405 | HIGH: Roof work | N62473-19-D-2620 22F4372 | Falling from Heights | J Davis Roofing | 2022-08-17 | 2022-08-17 | M | S | M | ESD: 08/23/2022 ECD: 10/31/2022 | Replace entire roof PH-1405. FEAD will conduct daily Safety Oversight. Contractor will follow the GDA accepted AHA. Ross 10/18/2022. | CONTINUING
PM-36 Roof | HIGH: Roof work | N62473-19-D-2620 22F4651 | Falling from Heights | J Davis Roofing | 2022-08-17 | 2022-08-17 | M | S | M | ESD: 08/17/2022 ECD: 11/11/2022 | Replace entire north roof section and remove abandoned air conditioning shed. FEAD will conduct daily Safety Oversight. Contractor will follow the GDA accepted AHA. Ross 10/18/2022 | CONTINUING
Note on L7: Keiser, Lucas E LT USN NAVFAC SW SAN CA (USA): Need to follow up on this activite

## In-House
PWD/SDMPO/FEAD/ROICC | Highest Risk Activities | Specific Project | Specific Risk | In-house Work Group | Date Leader's brief completed | Date JHA associated training completed by workers | Severity | Probability | RAC | Estimated start & completion | Comments (Navy oversight, controls/mitigations, etc.) | New or "Continuing" construction
PWD-NORCO Production | Working on A.C Equipment and Air Handlers | Bldg# 544 W.O # G3P3PB Making adjustments to A.C air flow and temp. controls | Falling from height, elect.Shock, electrocution | Shop Supervisor WRSP55 | 2020-07-27 | 2020-07-27 | III | D | 4 | 2020-07-27 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. | Completed
PWD-NORCO Production | Working and on A.C Equipment and Air handlers | Bldg # 507 W.O # G3P3NL checking A.C not working | Falling from unlevel ground, pavement, Elect. Shock, electrocution | Shop Supervisor WRSP55 | 2020-07-27 | 2028-02-27 | III | D | 4 | 2020-07-28 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. Use ground guides for AWP and operatord to wear Safety Harness | Completed
PWD-NORCO Production | Working off of plantform and securing electrieal power | Bldg#605 FGB6SD,replaceing suckion pump check valves and fitting | Falling from height or Shock hazard | Shop Supervisor WRSP55 | 2020-07-28 | 2020-07-28 | III | D | 4 | 2020-07-29 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. | Completed
PWD-NORCO Production | REPAIR LIGHTS NOT WORKING | Bldg # 510 W.O # FYJFNL Repairing lighting in restroom | Falling from height, elect. Shock electrocution slip hazards | Shop Supervisor WRSP55 | 2020-07-29 | 2020-07-29 | III | D | 4 | 2020-07-30 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. Use ground guides for AWP Scissor Lifts and operators to wear Safety Harness. | Completed
PWD -NORCO Production | INSTALL NEW A.C ELETRICIAL CONTACTOR | Replacing Photo Cells and Street Lighting Fixtures. WO#FSFVW7 | Falling from height or electrocution | Shop Supervisor WRSP55 | 2020-07-28 | 7/28/22020 | III | D | 4 | 2020-07-29 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. Use ground guides for Bucket Truck and operator to wear Safety Harness. | Completed
PWD-NORCO Production | Working on A.C Equipment and Air Handlers | Bldg# 505 w.o GFGMFH REPAIRING A.C NOT WORKING | SLIP,ELECTRICAL SHOCK | Shop Supervisor WRSP55 | 2020-12-07 | 2020-12-07 | III | D | 4 | 2020-12-07 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. | Completed
PWD-NORCO Production | REPAIR LIGHTING OUTSIDE OF BUILDING | Bldg# 512 replace lamps,fixures | Falling from ladders or electrocution | Shop Supervisor WRSP55 | 2020-12-11 | 2020-12-11 | III | D | 4 | 2020-12-11 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. Use ground guides for Bucket Truck and operator to wear Safety Harness. | Completed
PWD-NORCO Production | RPAIR GATE FALLING OVER | W.O # WDXYWG Bld'g 634 install new brackets to support gate | falling from hall side, slips and falls | Shop Supervisor WRSP55 | 2020-12-09 | 2020-12-09 | III | D | 4 | 17/9/2020 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. Use Safety Harness to tie off. | Completed
PWD-NORCO Production | Repair water leak | W.O# GCSXXJ Digging Excavation area to fine water leak | slip and falls back injury, cuts | Shop Supervisor WRSP55 | 2020-12-07 | 2020-12-07 | III | D | 4 | 2020-12-08 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. Use ground guides for Bucket Truck and operator to wear Safety Harness. | Completed
PWD-NORCO Production | install new lighting brackets | w.o # GH6DKZ repaire lights falling away from building | falling from ladder slips and falls electrical shock | Shop Supervisor WRSP55 | 2021-01-06 | 2021-01-06 | III | D | 4 | 2021-01-06 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. Use ground guides for Bucket Truck and operator to wear Safety Harness. | Completed
PWD-NORCO Production | saw cutting concrete for new electrical connection | w.o # GFYX36 installing new elecrtical line to bld'g 499 | cuts, eye injury, slip and falls | Shop Supervisor WRSP55 | 2021-01-05 | 2021-01-11 | III | D | 4 | 2021-01-11 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and utilize LOTO if necessary. | Completed
PWD-NORCO Production | Working from ladder. Replacing lamps and ballasts on light fixtures | GGJDTT replace lamps and ballasts | falling from heigh or electrical shock | Shop Supervisor WRSP55 | 2021-01-04 | 2021-01-04 | III | D | 4 | 1/4 TO 1-5 | ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, AND UTILIZE LOTO IF necessary | Completed
PWD-NORCO Production | Working from ladder repairing water leak | repair water leak | falling from ladder slips and falls | Shop Supervisor WRSP55 | 2021-01-04 | 2021-01-04 | III | D | 4 | 2021-01-04 | Ensure employees attend Pre Job Safety Brief, take all necessary Safety Precautions to include wearing all required PPE, and Utilize LOTO IF necessary | Completed
PWD-NORCO Production | replacing blower motor | install new a.c motor | electrical shock, cuts | Shop Supervisor WRSP55 | 2021-01-05 | 2021-01-05 | III | D | 4 | 2021-01-05 | Ensure employees attend Pre Job Safety Brief, take all necessary Safey Precautions to include wearing all required PPE, and Utilize LOTO if necessary | Completed
MPO | (1) Dropped load. (2) Overload of rigging gear resulting in damage. (3) Damage to high cost equipment. (4) Pinch Points. (5) Strains, sprains, trips and falls. (6) Man overboard. (7) Working with blended crews. (8) Ensure proper fall protection and fall protection plan are in place. | NAVFAC C&R - Install Jib and Weight Test Mobile Crane 8205874 at NBSD Crane Lot (Over 90%). | Personnel Injury | WRRP7F | 2022-10-18 | On Site | III | C | 4 | Start: 10/18/2022 End: 10/20/2022 | (1) OSHA approved Steel toe shoes, hard hats, gloves, reflective vests and safety glasses shall be utilized. (2) Caution and awareness to positioning of personnel throughout the entire evolution is essential. (3) Crane operator, RIC and the Tech Rep shall maintain constant communications throughout lifting operations. (4) Unauthorized personnel shall remain at safe distances away from lifting operations and out of the crane envelope. (5) Management shall be notified of any changes to JHA procedure (6) 1st line supervisor, Lonnie Cornaire/William Mewborn will be notified of any changes or issues. (7) If personnel baskets are utilized, a complex lift checklist will be performed prior to executing lift | New
MPO | (1) Dropped load. (2) Overload of rigging gear resulting in damage. (3) Damage to high cost equipment. (4) Pinch Points. (5) Strains, sprains, trips and falls. (6) Man overboard. (7) Working with blended crews. (8) Ensure proper fall protection and fall protection plan are in place. | USS Carl Vinson - Blue Portal-20 Crane Offload Tilly Crash Crane from Flight Deck on Juliett Pier at NASNI (Over 90%). | Personnel Injury | WRRP7C | 2022-10-18 | On Site | III | C | 4 | Start: 10/18/2022 End: 10/18/2022 | (1) OSHA approved Steel toe shoes, hard hats, gloves, reflective vests and safety glasses shall be utilized. (2) Caution and awareness to positioning of personnel throughout the entire evolution is essential. (3) Crane operator, RIC and the Tech Rep shall maintain constant communications throughout lifting operations. (4) Unauthorized personnel shall remain at safe distances away from lifting operations and out of the crane envelope. (5) Management shall be notified of any changes to JHA procedure (6) 1st line supervisor, Eddie Ramos/Johnny Bailey, will be notified of any changes or issues. (7) If personnel baskets are utilized, a complex lift checklist will be performed prior to executing lift | New
PWD Lemoore North | Hot Work / Airfield Maint. | WO: HFPNBV Bldg. 240 - Remove deck plate on aircraft parking apron and repair concrete | Burn/Fire Hazard ¦ FOD Hazard | In-house | 2022-03-15 | 2022-03-15 | III | D | 4 | 3/14/22 - 3/9/23 | Shop Supervisor/Leader will conduct safety brief and JHA training prior to work being started. Hot work permit will be obtained by prior to starting hot work activities. Fire prevention measures will be in place during hot work activities (fire extinguisher, fire blankets, etc.) Fire watch will be posted for 1-hour after hot work has been completed. Workers shall review JHA, wear all proper PPE, and briefed daily to adhere to the activities for the day. There will be a pre-use inspection of vehicles and PPE. All personnel shall wear proper PPE and follow all SOP's in accordance with the NASLEMRINST 3710.1 - Air Operations manual. Concrete maintenance and repair procedures will be conducted in compliance with UFC 3-270-01. All personnel shall wear proper PPE and follow all safety SOP's in accordance with the OPNAVINST 5100.23 H. | Continuing
PWD Lemoore North | AWP / Electrical | WO: HLZ4DY Bldg. 140 - Replace exterior lights | Fall Hazard / Shock Hazard | In-house | 2022-10-14 | 2022-10-14 | II | D | 4 | 9/30/22 - 10/30/22 | Shop Supervisor/Leader will conduct safety brief and JHA training prior to work being started. There will be a pre-use inspection of vehicles and PPE. Workers will employ appropriate fall protection, PPE, and spotters. Employees shall follow approved Fall Hazard Assessment and safety procedures in accordance with Fall Protection Program OPNAVINST 5100.13 and PWBL SW AWP SAFE 003.01. All personnel shall wear proper PPE and follow all safety SOP's in accordance with the OPNAVINST 5100.23 H. | Continuing
PWD Lemoore North | Electrical / Airfield Maint. | WO: HLXFMT RWY 32L - Repair airfield lighting fixtures | Shock Hazard ¦ FOD Hazard | In-house | 2022-10-21 | 2022-10-21 | II | D | 4 | 9/22/22 - 10/22/22 | Shop Supervisor/Leader will conduct safety brief and JHA training prior to work being started. There will be a pre-use inspection of vehicles and PPE. Workers will employ appropriate fall protection, PPE, and spotters. Electricians will ensure that power is secured by Switching Orders if applicable. They will use proper lock-out/tag-out and grounding procedures to avoid contact with live circuits. Arc flash/ electrical rated PPE shall be worn. Electricians are to follow safety guidelines in accordance with PWBL SW ESAFE 001.02. All personnel shall wear proper PPE and follow all safety SOP's in accordance with the OPNAVINST 5100.23 H. | New
PWD Lemoore North | E-28 Arresting Gear ¦ Hot Work ¦ Runway Hazards | WO: FTLB9W RWY 32R/32L - Repair E-28 Arresting Gear | Burn/Fire Hazard ¦ Impact/Crush Hazard ¦ Aircraft Hazard ¦ FOD Hazard | In-house | 2022-07-11 | 2022-07-11 | II | D | 4 | 4/09/20 - TBD | Shop Supervisor/Leader will conduct safety brief and JHA training prior to work being started. Hot work permit will be obtained by prior to starting hot work activities. Fire prevention measures will be in place during hot work activities (fire extinguisher, fire blankets, etc.) Fire watch will be posted for 1-hour after hot work has been completed. Workers shall review JHA, wear all proper PPE, and briefed daily to adhere to the activities for the day. There will be a pre-use inspection of vehicles and PPE. All personnel shall wear proper PPE and follow all SOP's in accordance with the NASLEMRINST 3710.1 - Air Operations manual. Concrete maintenance and repair procedures will be conducted in compliance with UFC 3-270-01. All personnel shall wear proper PPE and follow all safety SOP's in accordance with the OPNAVINST 5100.23 H. | Continuing
PWD Lemoore South | Working from heights | HLYX7Y | Falling from heights | In-house | 2022-10-18 | 2022-10-18 | II | C | 4 | 2022-10-18 | Pre-op inspection of equipment and PPE. Spotter will be used. Follow fall hazard assessment and safety procedures. | NEW
PWD Lemoore UEM | USE OF BUCKET TRUCK | Repair/replace parking and street lights in ADMIN/HOUSING/OPS (as-needed maintenance) | Fall from height Electrical Shock /Burns | In-house | 2022-10-17 | 2022-10-17 | II | C | 3 | ONGOING | Shop Supervisor/Leader will conduct JHA training prior to work being started. The Bucket Truck will be used to remove, replace or repair Parking and Street lights. There will be a pre-use inspection of vehicles and PPE. Workers will employ appropriate fall protection, PPE, and spotters. Follow approved Fall Hazard Assessment and safety procedures applicable | CONTINUING
PWD Lemoore UEM | High Pressure Air System | DAILY PM BLDG 50 | High Pressure Air | In-house | 2022-10-17 | 2022-10-17 | III | C | 4 | ONGOING | Shop Supervisor/Leader will conduct JHA job brief prior to work being started. All persons involved will use the appropriate PPE and preform LOTO and relieve the system pressure. | CONTINUING
PWD Lemoore UEM | Sewage System | Weekly/Monthly PM ADMIN/HOUSING/OPS | Exposure to methane gas and sewage | In-house | 2022-10-17 | 2022-10-17 | III | C | 4 | ONGOING | Shop Supervisor/Leader will conduct JHA training prior to work being started. All persons involved will use the appropriate PPE and preform LOTO at lift stations as necessary. | CONTINUING
PWD Lemoore UEM | Trenching /Excavation | Repair Water Leak/Break | Slip/Fall/ Cave-in | In-house | 2022-10-17 | 2022-10-17 | II | C | 3 | ONGOING | The shop Supervisor/Leader will conduct the JHA training along with job lead prior to any work being started. The excavation will be overseen by a trained competent trenching person to insure all appropriate guidelines are followed. All persons involved will use the appropriate PPE. | CONTINUING
PWD Lemoore UEM | HV Electrical Work | POWER OUTAGE | Electrical Shock/ Burns | In-house | 2022-10-17 | 2022-10-17 | II | C | 3 | ONGOING | Shop Supervisor/Leader will conduct JHA training prior to work being started. Electricians will ensure that power is secured by Switching Orders. They will use proper lock-out/tag-out and Grounding procedures to avoid contact with live circuits. | CONTINUING
PWD Lemoore UEM | HV Electrical Work | PM HV Electrical | Electrical Shock/ Burns | In-house | 2022-10-17 | 2022-10-17 | II | C | 3 | ONGOING | Shop Supervisor/Leader will conduct JHA training prior to work being started. Electricians will ensure that power is secured by Switching Orders. They will use proper lock-out/tag-out and Grounding procedures to avoid contact with live circuits. | CONTINUING
PWD Lemoore Projects | Demolition & Construction | WO: HJJY3B Bldg. 951 - MWR - Convert storage area in to outdoor NOFFS | Multiple Hazards: Fall/ Trip/ Impact/ Puncture/ Electrical, Heavy Equipment | In-house | 2022-06-21 | 2022-06-21 | II | D | 4 | 6/21/22 - 11/30/22 | Shop Supervisor/Leader will conduct safety brief and JHA training prior to work being started. There will be a pre-use inspection of vehicles and PPE. Workers will employ appropriate fall protection, PPE, and spotters. Employees shall follow approved Fall Hazard Assessment and safety procedures in accordance with Fall Protection Program OPNAVINST 5100.13 and PWBL SW AWP SAFE 003.01. Electricians will ensure that power is secured by Switching Orders if applicable. They will use proper lock-out/tag-out and grounding procedures to avoid contact with live circuits. Arc flash/ electrical rated PPE shall be worn. Electricians are to follow safety guidelines in accordance with PWBL SW ESAFE 001.02. All personnel shall wear proper PPE and follow all safety SOP's in accordance with the OPNAVINST 5100.23 H. | Continuing
PWD Lemoore Projects | Demolition & Construction | WO: HKTHYX Bldg. 270 - Mods 3 - Renovate Ready Rooms (SAPF) | Multiple Hazards: Fall/ Trip/ Impact/ Puncture/ Electrical, Heavy Equipment | In-house | 2022-08-08 | 2022-08-08 | II | D | 4 | 8/8/22 - 8/3/2023 | Shop Supervisor/Leader will conduct safety brief and JHA training prior to work being started. There will be a pre-use inspection of vehicles and PPE. Workers will employ appropriate fall protection, PPE, and spotters. Employees shall follow approved Fall Hazard Assessment and safety procedures in accordance with Fall Protection Program OPNAVINST 5100.13 and PWBL SW AWP SAFE 003.01. Electricians will ensure that power is secured by Switching Orders if applicable. They will use proper lock-out/tag-out and grounding procedures to avoid contact with live circuits. Arc flash/ electrical rated PPE shall be worn. Electricians are to follow safety guidelines in accordance with PWBL SW ESAFE 001.02. All personnel shall wear proper PPE and follow all safety SOP's in accordance with the OPNAVINST 5100.23 H. | Continuing
PWD NBSD | Routine Preventive HVAC, AC, POOL and FIRE systems Maintenance tasks. | Recurring Maintenance tasks on multiple HVAC and AC systems, Pools, Spas, Ventilation and Fire systems conducted at Multiple Buildings as scheduled in the Maximo PM package | Injury from Slips, Trips, Falls, using step ladders, low voltage electrical shocks, Solvents and lubrication exposure, noise exposure above 85dba. | NBSD RECURRING MAINTENANCE WRDP52 | DAILY JHA COMPLETION | JHA TRAINING CONDUCTED 4/20/22 AND REVIEWED WEEKLY | III MINOR | D UNLIKELY | 5 NEGLIGIBLE | DAILY WEEKDAYS | PERSONAL PPE WILL BE WORN AT ALL TIMES. PROPER FALL PROTECTION WILL BE WORN AS REQUIRED. JHA WILL BE GENERATED AND REVIEWED BY ALL WORKERS. SCAFFOLD WILL BE CHECKED DAILY BY CP BEFORE USE. TOOLS WILL BE TETHERED TO PREVENT FALLING. ENERGY LOCKOUT / TAGOUT WILL BE IN EFFECT WHEN REQUIRED. LADDER SAFETY INSPECTIONS WILL BE COMPLETED BEFORE USE. AFFECTED PERSONNEL SAFETY BOUNDARIES WILL BE ESTABLISHED AS REQUIRED. SDS FOR LUBES AND SOLVENTS WILL BE ON HAND AND REVIEWED AS REQUIRED. | CONT
PWD China Lake | Excavation | Murray Middle school | Trench Cave In | UEM Distribuition | 2022-10-17 | 2022-10-17 | III | C | 4 | 2022-10-17 | Competent Excavation and Trenching Person, All PPE to be used - JHA to be followed. | NEW
PWD China Lake | Excavation | P1911 project | Trench Cave In | UEM Distribuition | 2022-10-17 | 2022-10-17 | III | C | 4 | 2022-10-17 | Competent Excavation and Trenching Person, All PPE to be used - JHA to be followed. | NEW
PWD China Lake | Testing for Power | Check Voltage CKT NS 2 | Physical Hazards | UEM HV Shop | 2022-10-17 | 2022-10-17 | II | C | 3 | 2022-10-17 | Shop supervisor will conduct JHA training prior to work being started. SOP/Esafe energizing-de-energizing location in S-Drive. There will be a pre-use inspection of vehicles and PPE. Workers will employ appropriate PPE and spotters. | NEW
PWD China Lake | Testing for Power | Check Voltage CKT FH18 | Physical Hazards | UEM HV Shop | 2022-10-19 | 2022-10-19 | II | C | 3 | 2022-10-19 | Shop supervisor will conduct JHA training prior to work being started. SOP/Esafe energizing-de-energizing location in S-Drive. There will be a pre-use inspection of vehicles and PPE. Workers will employ appropriate PPE and spotters. | NEW
PWD China Lake | Use of Ladders | Multilple Projects at VariousFacilities, while performing HVAC, lighting, fire alarm PM's and project work. | Fall from height | WR2P52 WR2P53 WR2P54 | 10/17/2022- 10/21/2022 Daily | 10/17/2022- 10/21/2022 Daily | II | C | 3 | 10/17/2022- 10/21/2022 Daily | Shop supervisor will conduct JHA training prior to work being started. The LADDER will be used to reach overhead lights attached to ceiling . There will be a pre-use inspection. Workers will employ appropriate fall protection, PPE. | Continuing
PWD China Lake | Thermal Stress | everyday work environment | Heat exhaustion/stroke | WR2P52 WR2P53 WR2P54 | 10/17/2022- 10/21/2022 Daily | 10/17/2022- 10/21/2022 Daily | II | C | 3 | 10/17/2022- 10/21/2022 Daily | All personell to have plenty of water resources on work site. | Continuing
PWD China Lake | Electrical Work | everyday work environment | Electrical Shock | WR2P52 WR2P53 WR2P54 | 10/17/2022- 10/21/2022 Daily | 10/17/2022- 10/21/2022 Daily | II | C | 3 | 10/17/2022- 10/21/2022 Daily | Shop supervisor will conduct JHA training prior to work being started. Electrical Work will be preformed on many different types of electrcal components. There will be a pre-use inspection. Workers will employ appropriate electrical safety procedure ,and PPE. All personnel will utilize JHA and propoer lock out procedures as required by E-Safe Program for all electrical work. | Continuing
PWD China Lake | Anything Requiring PPE | everyday work environment | Injury to Wokers | WR2P52 WR2P53 WR2P54 | 10/17/2022- 10/21/2022 Daily | 10/17/2022- 10/21/2022 Daily | II | C | 3 | 10/17/2022- 10/21/2022 Daily | Shop supervisor will conduct JHA training prior to work being started. Work that requires PPE will be preformed. Workers will employ appropriate PPE for the work being performed. | Continuing
PWD China Lake | Use of AWP | Ongoing crane inspections Buildings, 00991, 12140 Others TBA | Fall from height | Transportation crane section | 2022-10-17 | 2022-10-17 | ll | D | 4 | 2022-10-17 | All PPE to be used - JHA to be followed Location TBD by fundingü Install physical barriers. | Continuing
PWD China Lake | Use of Ladders | Ongoing crane inspections Buildings, 00991, 12140 Others TBA | Fall from height | Transportation crane section | 2022-10-17 | 2022-10-17 | lll | D | 5 | 2022-10-17 | All PPE to be used, FP only when needed and attachment points are available - JHA to be followed Location TBD by funding ü Install physical barriers. | Continuing
PWD China Lake | Use of Lifting Gear | Ongoing crane inspections Buildings, 00991, 12140 Others TBA | Dropped weights / pinch points / damage to equipment | Transportation crane section | 2022-10-17 | 2022-10-17 | lll | D | 5 | 2022-10-17 | All PPE to be used - JHA to be followed Location TBD by funding and certification requirements | Continuing
PWD China Lake | Crane envelope | Ongoing crane inspections Buildings, 00991, 12140 Others TBA | Contact with objects dropped loads | Transportation crane section | 2022-10-17 | 2022-10-17 | lll | D | 5 | 2022-10-17 | Use JHA to assist in locating any objects that will be in the crane path.ü Install physical barriers. | New
PWD China Lake | Lock out tag out | Ongoing crane inspections Buildings, 00991, 12140 Others TBA | Electric shock | Transportation crane section | 2022-10-17 | 2022-10-17 | lll | D | 5 | 2022-10-17 | Use JHA for Lock out / Tag out. Follow all procedures as trained use required PPE as assigned | Continuing
PWD Point Loma | Working in occupied spaces and at times around other employees where social distancing cannot be maintained | All Work | Potential for exposure to COVID-19 | All shops | 2022-10-18 | 2020-03-17 | II | C | 3 | 1/1/22- 12/31/22 | Wash hands frequently, avoid personnel exhibiting flu symptoms, stay home if sick, and maintain Tactical Separation. Separated (Blue/Gold teams) for WG employees use 245 326 and MCASM-6311, 6340. Use latex gloves, hand sanitizer, and wipes (2 month supply on-hand). Adjusted work procedures to minimize personnel potentially identified in the event of contact tracing by creating two-person teams when work can not be completed utilizing tactical separation. Transition to HPCON A Reverse COOP Phase 3 Return to the Workplace 6/5/22 COMPLETE. 9/20/22 - per new instruction, testing of un-vaccinated and requesting vaccination status of visitors NOT required. | Continuing
PWD Point Loma | Excavating using skid steer. | HD# 550; WO #HKR7BZ; Replace raised sidewalk. | Strains, cuts, bumps, bruises. | Project Shop WRZP54 Supervisor Stoyan Markov 764-9370 | 2022-10-18 | 2022-10-18 | II | C | 3 | 10/18/2022 -11/15/2022 | Complete JHA and have supervisor review. PPE will include hard hat, vest, safety shoes . A Excavation and trenching competent person will be all the time on site.. A skid steer pre-use inspection sheet will be completed by the operator before use. Technician will barricade and block off access to working area and will use spotter on the ground at all times. The Shops Supervisor will arrange a Pre-Con. The Client, Project Manager, Journeyman and Engineering Tech shall attend. The Supervisor will spot check job periodically after initial start up. | NEW
PWD Point Loma | Electric shock Working on a AWP | B#560N, WO#HCMSLK; Replace parking lot lights and two light pole. | Electric Shock, Fall from Heights. Strains, cuts, bumps, bruises. | Project Shop WRZP54 Supervisor Stoyan Markov 764-9370 | 2022-10-18 | 2022-10-18 | II | C | 3 | 10/18/2022 -12/8/2022 | Complete JHA and have supervisor review. ESAFE 001 procedures will be followed at all times. SAFE 003.01 ( Operations of Arial Work Platform (AWP)) procedures will be followed at all times .Lock out/tag out will be used for electric circuit. A lock out/tag out form will be completed and reviewed by supervisor. PPE will include, hard hat, vest, safety shoes, safety glasses, harness, arc flash face shield and electrical rubber gloves . A fall protection plan will be completed by a competent person. A rescue plan will be completed by a competent person. A lift pre-use inspection sheet will be completed by the operator before use. Technician will barricade and block off access to working area and will use spotter on the ground at all times . A Excavation and trenching competent person will be all the time on site. The Shops Supervisor will arrange a Pre-Con. The Client, Project Manager, Journeyman and Engineering Tech shall attend. The Supervisor will spot check job periodically after initial start up. | NEW
PWD Point Loma | Operating high pressure water jet equipment | Old Town complex; WO#HLZCHG; Water jetting restrooms on multiple locations in Old town complex. | Strains, cuts, bumps, bruises. | Project Shop WRZP54 Supervisor Stoyan Markov 764-9370 | 2022-10-18 | 2022-10-13 | II | C | 3 | 10/13/2022 - 9/30/2023 | Complete JHA and have supervisor review. MSAFE 001 procedures will be followed at all times. PPE will include, vest, safety shoes safety glasses. The Shops Supervisor will arrange a Pre-Con. The Client, Project Manager, Journeyman and Engineering Tech shall attend. The Supervisor will spot check job periodically after initial start up. | NEW
PWD Point Loma | Working at heights on AWP | NBPL-570 WO#HMMXZY Repairing/ replacing overhead and exterior parking lot lights | Electrical shock, fall from heights, slips, trips | E/S Shop WRZP53 Supervisors Arlin Somers 619-764-9196/ | 2022-10-18 | 2022-10-20 | II | C | 3 | 2022-10-21 | PPE will include vest, glasses, safety shoes. Ladders will be used for overhead work. Follow proper ladder safety at all times. Complete JHA and have supervisor review. MUTIPLY LOCKOUT TAG OUT | New
PWD Point Loma | Working at heights on AWP | NBPL-5 Coast Guard WO# HMND6Y Repairing/ replacing overhead and exterior parking lot lights | Electrical shock, fall from heights, slips, trips | E/S Shop WRZP53 Supervisors Arlin Somers 619-764-9196/ | 2022-10-18 | 2022-10-21 | II | C | 3 | 2022-10-22 | PPE will include vest, glasses, safety shoes. Ladders will be used for overhead work. Follow proper ladder safety at all times. Complete JHA and have supervisor review. MUTIPLY LOCKOUT TAG OUT | New
PWD Point Loma | Working at heights on AWP | NBPL-32 WO#HMNCWT Repairing/ replacing overhead and exterior parking lot lights | Electrical shock, fall from heights, slips, trips | E/S Shop WRZP53 Supervisors Arlin Somers 619-764-9196/ | 2022-10-18 | 2022-10-27 | II | C | 3 | 2022-10-28 | PPE will include vest, glasses, safety shoes. Ladders will be used for overhead work. Follow proper ladder safety at all times. Complete JHA and have supervisor review. MUTIPLY LOCKOUT TAG OUT | New
Receiving and Unloading of Barge on SNI | SNI Barge Operations (Navy and Contractor Barge) NAVAIR | Receiving and Unloading of Barge on SNI | Crushing by vehicle | In-House | Scheduled for TBD | Scheduled for TBD | II | C | 3 | Scheduled for TBD | Barge Operations require large vehicle operation in close proximity to personnel on barge/ramp/pier. Mitigation through wearing of PPE (vests), employment of spotter, limiting personnel foot traffic on barge ramp, and heighted awareness through safety brief. Transportation employee, Chris Willard, will supervise vehicle operations through the evolution. Note: PWD VC employee Jimmy Lenwell will be fall protection competent person for the evolution. | New Recurring
PWD PH-Wharf-5 | Crane Operations | Crane support for the reconfiguration of the MST | Dropped Load | In-House | Scheduled for Sept 26-30, 2022 | Scheduled for Sept 26-30, 2022 | II | C | 3 | Scheduled for Sept 26-30, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PWD PH-Wharf-4 | Crane Operations | Crane support for departure of the USS Gridley shore power cables | Dropped Load | In-House | Scheduled for Sept 27, 2022 | Scheduled for Sept 27, 2022 | II | C | 3 | Scheduled for Sept 27, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PWD PH- Bldg. 1100 | Crane Operations | Crane support for EXWC offload generator | Dropped Load | In-House | Scheduled for Sept. 28, 2022 | Scheduled for Sept. 28, 2022 | II | C | 3 | Scheduled for Sept. 28, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PWD PH-Wharf-5 | Crane Operations | Crane support for USV Ranger on loaf misc. items | Dropped Load | In-House | Scheduled for Sept. 29, 2022 | Scheduled for Sept. 29, 2022 | II | C | 3 | Scheduled for Sept. 29, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PWD SNI | Crane Operations | Crane HTC 8690 N82-05620 Recertification | Dropped Load | In-House | Scheduled for Oct. 3-4, 2022 | Scheduled for Oct. 3-4, 2022 | II | C | 3 | Scheduled for Oct. 3-4, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PWD PH-Wharf-5 | Crane Operations | Crane support for USV Ranger on loaf misc. items | Dropped Load | In-House | Scheduled for Oct. 7, 2022 | Scheduled for Oct. 7, 2022 | II | C | 3 | Scheduled for Oct. 7, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PWD PH-Wharf-5 | Crane Operations | Crane support for USV Ranger on loaf misc. items | Dropped Load | In-House | Scheduled for Oct. 10, 2022 | Scheduled for Oct. 10, 2022 | II | C | 3 | Scheduled for Oct. 10, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PWD PH-Wharf-4 | Crane Operations | Crane support for Arrival of the USS Harpers Ferry shore power cables | Dropped Load | In-House | Scheduled for Oct. 17, 2022 | Scheduled for Oct. 17, 2022 | II | C | 3 | Scheduled for Oct. 17, 2022 | Crane operator and riggers are all qualified to perform the line handling and will utilize the SOP as required. Rigger-IN-Charge will conduct the pre-lift brief and JHA. | New Recurring
PM362 and PH1392 | Crane Maintenance | BSV&E MITC Overhead Crane Maintenance | Fall from Heights | In-House | Scheduled for 9-01-2022 THRU 9-30-2022 | Scheduled for 9-01-2022 THRU 9-30-2022 | I | D | 3 | Scheduled for 9-01-2022 THRU 9-30-2022 | Crane Mechanics and Inspectors are all qualified to perform the service and will utilize the P-307. The Crane/Inspector, Michael Vose will supervise the evolution, fall protection plan and conduct the pre-lift brief. | New